# Implementation of 
the Public Financial Management Roadmap II – The Inaugural 5-Year Rolling plan

Ministry of Finance Delivering:

Efficient and effective public services;

Strong fiscal discipline; and

Strategic fiscal policy

Abstract

This is the inaugural 5-year rolling Fiscal Performance Improvement Plan by the Government of Afghanistan. It is the vehicle for the implementation of the Public Finance Management Roadmap II and presents a sequenced team based plan for reforms within a performance management framework.

The development of this plan has been a Government driven process with a high degree of ownership over the proposed reforms. The Government recognizes that improvement in fiscal planning and management is crucial for the long-term development of Afghanistan. This plan covers the full spectrum of reforms, from developing a fiscal policy framework to guide the budget, to improved reporting and audit of public expenditure.

Ministry of Finance

Kabul, Afghanistan

February 2016

TAble of
Contents

Executive Summary	1

Introduction	6

Afghanistan’s inaugural 5-Year Rolling plan	7

A Team Based Performance Management Approach	7

Team-Led Reforms – Every Team Matters	13

Teams within Teams – Participating Agencies	14

The Flagship Reforms – Taking on the Big Challenges	15

Aspirational Targets – Our Guides	19

Staffing Priorities – Technical Assistance Gaps	33

Financing – Gaps	33

Government’s Sector Budget Support Policy Framework	36

Attachments	38

Attachment A: 5 Year Plans	39

Attachment B: Aspirational and Guiding Targets to support Implementation of the PFMR-II	40

Attachment C: “Basics first”	61

Attachment D: Budget Support Policy Framework	62

Attachment E: Costings and Resource Allocations	69

TAbleS

Table 1.	Current Participating Agencies	14

Table 2.	Flagship Reforms of the Teams	18

Table 3.	DB Taxes & Customs: Proposed Aspirational Targets (100 Best)	25

Table 4.	Tax Payments and Times	25

Table 5.	Customs Documents and Times	25

Table 6.	Frequency of Risk Impact Dimensions	29

Table 7.	Medium Term Resourcing Allocations – Economic & Function (US$)	35

Table 8.	Medium Term Resourcing Costings – by Administrative Unit (US$)	36

Table 9.	Aspirational PEFA Targets	40

Table 10.	Aspirational Targets for Selected Upgraded PEFA Indicators	44

Table 11.	Aspirational OBI Targets	53

Table 12.	Statistical Capacity Indicators	60

Table 13.	Explanations of Sector Budget Support Design Elements	63

Table 14.	Costings by Directorate (US$)	69

Table 15.	Medium Term Costings by Economic Classification (US$)	72

Table 16.	Medium Term Costings by Function Classification (US$)	72

Figures

Figure 1.	The Continuous Performance Improvement Cycle	10

Figure 2.	The 2016 – 17 Performance Management Cycle	13

Figure 3.	Aspirational Targets for PEFA and PEFA-10	20

Figure 4.	Selected Aspirational Targets for Upgraded PEFA	21

Figure 5.	Aspirational Targets for Open Budget Index	22

Figure 6.	Aspirational Targets for Statistical Capacities	23

Figure 7.	Doing Business: Proposed Aspirational Ranks (100 Best)	23

Figure 8.	Trends in Tax Collection – Selected Comparators	24

Figure 9.	Budget and Treasury: Solving Systemic Problems	27

Figure 10.	Risk-Return (performance and TA) Space	29

Figure 11.	Time Required and Coordination Requirements of Activities	30

Figure 12.	Risk-Return (& TA) Space Selected PFM Reform Driving Teams	31

Figure 13.	Revenue Generating Agencies: Risk-Return Space	32

Figure 14.	Admin and Finance: Risk-Return (performance and TA) Space	32

Figure 15.	Fiscal Performance Improvement Costs (Shares & US$)	35

bOXES

Box 1.	Why Team Based Performance Matters	7

Box 2.	The Seven Goals for Performance Management:	8

Box 3.	Summary of Design Elements for the Budget Support Framework:	63

ACRONYMS

| AD | Admin Department |
| --- | --- |
| AEITI | Afghanistan Extractives Transparency Initiative |
| AFMIS | Afghanistan Financial Management System |
| AMD | Aid Management Directorate |
| ARAZI or AILA | Afghanistan Independent Land Authority |
| ARTF | Afghanistan Reconstruction Fund |
| ASI | Adam Smith International |
| BD | Budget Department |
| CBR | Capacity Building for Results |
| CD | Customs Department |
| CSO | Central Statistics Office |
| DFID | Department for International Development (UK) |
| GDP | Gross Domestic Product |
| GoIRA | Government of the Islamic Republic of Afghanistan |
| HR | Human Resources |
| HRD | Human Resources Department |
| IAD | Internal Audit Department |
| ID | Insurance Department |
| IDLG | Independent Directorate of Local Governance |
| IT | Information Technology |
| MAIL | Ministry of Agriculture Irrigation and Livestock |
| MARGD | Monitoring, Analysis and Reporting General Directorate |
| MBAW | Making Budgets and Aid Work |
| MFPD | Macroeconomic and Fiscal Performance Department |
| MOF | Ministry of Finance |
| NPA | National Procurement Authority |
| OBI | Open Budget Index |
| OoM | Office of the Minister |
| PD | Property Department |
| PEFA | Public Expenditure and Financial Accountability |
| PFM | Public Financial Management |
| PICGD | Programs Implementation and Coordination General Directorate |
| PMT | Performance Management Team |
| RD | Revenues Department |
| RIMU | Reform Implementation Management Unit |
| RPD | Revenue Planning Department |
| SABII | Strengthening Afghanistan’s Budget II |
| SAO | Supreme Audit Office |
| SD | SOE Department |
| TA | Technical Assistance |
| TD | Treasury Department |
| UNDP | United National Development Program |
| US$ | United States Dollar |
| USAID | United States Agency for International Development |

For PEFA related terms please refer to PEFA Guidance.

# Executive Summary

This is the inaugural 5-year rolling Fiscal Performance Improvement Plan by the Government of Afghanistan. It is the vehicle for the implementation of the Public Finance Management Roadmap II and presents a sequenced team-based plan within a performance management framework.

The development of this plan has been a Government driven process with a high degree of ownership over the proposed reforms. The Government recognizes that improvement in fiscal planning and management is crucial for the long-term development of Afghanistan. This plan covers the full spectrum of reforms, from developing a fiscal policy framework to guide the budget, analysis of fiscal space, adopting a medium term expenditure framework with a consolidated national budget, improved cash management and commitment controls, with upgraded systems that integrate procurement, contract management and cash management, and improved reporting and audit of public expenditure.

The plan is starting with the core departments managing public financial management in the Ministry of Finance (MOF) and two external agencies, AEITI and the National Procurement Authority. Over the next 12 months, the plan will incorporate other key agencies such as the Supreme Audit Office, the Central Statistics Office and the Independent Directorate for Local Governance. The performance management framework will include key line ministries from 2017 with a focus on budget planning, execution and reporting.

This plan recognises that the challenges facing the Government in reforming public financial management are large and complex. Progress will take time and there will be set backs along the way. That is why this plan is set in a framework of 5-year rolling plans. Each year there will be a mid-year assessment of progress, an annual performance assessment with a published report on results, leading to a revised 5-year plan at the beginning of each year. This plan follows the budget cycle and integrates with the Government’s established business processes.

- Team-Based Performance Management

The Government has chosen a team-based performance management framework because we believe that teams are the engine room of Government policy. Building up the capacity of teams through genuine performance management will maximise returns for reform investments. This framework is international best practice and anchored by the principles of the New Deal for Conflict Affected and Fragile States established by the g7+ Group of countries.

The principle that every team matters underpins the Government’s approach. Much is made of efforts to build capacity in Afghanistan, but often neglects the corporate and institutional backbone of Government in favour of policy areas. In order to break the cycle of external dependence, the Government recognizes the need for more investment in areas like HR, finance, administration, IT and procurement.

Flagship Reforms

The complexity and enormity of this reform effort is evident in the team level 5-year rolling plans attached to this paper. There are 19 General Directorates and 63 Directorates in this inaugural plan. Each Directorate has identified around 10 to 12 activities to monitor and assess meaning the Government is implementing around 700 activities many of which have sub-activities. This is just the core agencies responsible for the PFM system, and does not yet include line ministries who actually spend the national budget. They will phase into the performance management system beginning in 2017.

This reflects a reality that is often lost when reforms are “projectised” and the focus is solely on strategic level outcomes. Government is big and complicated. Despite this complexity, it is incumbent on the Government to provide a coherent narrative on what this all means. This plan forms the basis of the PFM reforms outlined by the President and the Minister for Finance to the International Community in Kabul in late 2015. This plan will be the scorecard for when the Government next reports to its development partners later this year in Brussels.

Flagship reforms being targeted by the Government can be summarised under three broad headings:

  - Reforms to improve the performance of Government investments, leading to better economic outcomes

  - Reforms to ensure the budget is more accurate, transparent and free of corruption; and

  - Reforms to build the capacity of the state to manage reforms, beginning with investments in things like HR, administration, finance, IT and communications within the MOF.

The flagship reforms begin with improving the performance of investments leading to better economic outcomes. This reflects a number of key areas of the plan.

Firstly, the government has established a new Macroeconomic and Fiscal Performance Department (MFPD), reporting directly to the Minister for Finance. This is significant as this is the part of Government responsible for bringing revenue and expenditure estimates together and, based on economic parameters, presenting the fiscal outlook to the Cabinet. The MFPD 5-year plan focusses on making an improved fiscal space analysis the basis for Cabinet consideration of the priorities for the annual budget. It will also help underpin the creation of credible forward estimates. A statement of national priorities by the Government based on improved macroeconomic and fiscal analysis will guide and focus the preparation of the annual budget, laying the foundation for linking policy and budgets.

Secondly, the Government has established the Programs Implementation and Coordination General Directorate to support the Councils whose primary function is to guide national development priorities. This is in effect a Cabinet Secretariat role and their plan focusses on setting up robust procedures for managing the business of the councils. This will assist the Directorate General of Budget to direct budget submissions towards national priorities with a clear understanding of the fiscal space available for Government investment and the national development priorities.

A range of measures to ensure the accuracy, transparency and robustness of the budget will reinforce this improvement in the policy setting process at the start of the annual budget cycle. This will begin with efforts to introduce more systematic, accurate and rule-based costing of budget proposals piloting new approaches in the MOF before rolling them out to other Ministries. There will also be trials of reforms to the commitment control process to ensure the use of allotments is for their intended purpose. Improved forecasting and the establishment of rolling forward estimates will help to eliminate the systematic over estimation of both revenue and expenditure that has been a feature of the national budget over recent years. This is a key area of reform requiring attention if Afghanistan is to reach its aspirational targets under international benchmarks for good public financial management.

Treasury will make very large investments in the Afghanistan Financial Management System (AFMIS) to bed in important improvements to the management of expenditure. An upgraded AFMIS will link contract and procurement information to Treasury functions. This will combine with improved cash management and commitment controls to remove most of the points of discretion in the system that allow for corruption. The National Procurement Authority (NPA) will work with Treasury to ensure no payments to any project that has not met Government procurement standards. Similarly, contractors will receive no milestone payments unless the contract and milestones are on the system.

Budget reporting remains an area in need of significant improvement. As noted in the President’s PFM Assessment (March 2015) and in PEFA scores, it is not possible with existing systems to accurately compare the budget to the end of year financial accounts. The Government intends to move to a consolidated national budget in the longer-term with one currency and one accounting standard. In the shorter-tem, the Government will introduce ministerial budget statements at the beginning of the budget year and annual reports that compare budgets to actuals. Piloted in the MoF and rolled out to all line Ministries over the next few years. This improved reporting will not replace internal and external audit with the 2016 plan focussed on strengthening internal audit to meet international standards and building capacity for audit.

Revenue is an area that has already been a key focus for the Government, with significant improvements already achieved. This plan shows strong intent in both revenue and customs to increase revenue. The focus is on doing the basics first, expanding the reach of the revenue authorities and improving compliance. Policy measures will remain under consideration but the reach and capacity of the revenue and customs departments to administer the current system are the priority.

None of this will be possible unless the Government can improve its institutional capacity to manage the national budget. This plan contains significant measures to improve HR, IT, administration and especially internal budget and financial management processes. The Government will begin with the MoF and add in key line ministries over the next year or two. These reforms aim to reduce fiduciary risks and improve the performance of the Government. A good example is the policy of moving away from externally contracted staff towards more use of Capacity Building for Results (CBR) funds and making sure that all core positions are Tashkeel. External technical assistance will be still be needed but it will now be restricted to a small number of genuine gaps.

MoF will incorporate the detailed anti-corruption, currently under Cabinet consideration, into the plan at the mid-year assessment.

This policy reflects the Government’s decision not to seek to extend or replace the UNDP supported MBAW or the UK supported SABII in the short term. While these programs have made a significant contribution to the Government’s capacity, the Government focus is on putting in place long-term business plans, with sustainable staffing profiles with officials in all key positions. With this done, we can better target external support to meet the Government’s needs.

Reforms will be assessed through a range of custom designed outcomes and international benchmarks. In this plan, the Government has proposed an initial set of aspirational targets for PEFA, OBI, Statistical Capacity and Doing Business indicators. We expect to finalise these aspirational targets by the end of this year after which they will remain fixed over the next 5 years. The purpose of the aspirational targets it to ensure that the government is working towards best practice in public financial management as well as to provide a context for donor partners to compare progress.

- Risk Return Profile of proposed reforms

As might be expected, the risk return profile of this first 5-year plan is one where most activities are high impact but high risk. This profile shows that teams are prepared to take on the important reforms, but recognises that they will be a challenge. Careful monitoring through the performance management system will be required to ensure progress and that important reforms are not lagging.

- Staffing Priorities

The detailed 5-year plans attached to this paper reveal that much of the reform agenda is about actions being taken by teams, in other words by people. Teams have identified technical assistance gaps using a consistent methodology focussed on the underlying policy of moving away from external assistance towards self-reliance. In contrast to previous designs of projects to assist the Government, the focus is on teams and individual activities rather than thematic areas. For each proposed action, teams have identified the work done by either national or international technical assistance.

By systematically identifying where the TA is, and linking it to major actions under the reform plan, we now have a team level view of the needs. This has helped the Government to plan for moving long-term contractors over to Tashkeel, with CBR top ups where appropriate. We have made significant progress in this areas and the Government expects to see a steady move away from long-term TA towards support for skills gaps.

- Financing Gaps

Financing of this plan will also follow a different process to previous reform programs. Much of the work under the plan is core business undertaken by Government staff. As already noted, external assistance is being phased out to the extent possible and many positions are being transferred to Tashkeel with CBR top ups. This reduces the need for additional external financing. There are also some ongoing support programs, such as PFMR2 (World Bank), the Customs Reform Project (World Bank), support to the performance management system through a grant to the Institute of State Effectiveness (DFID and Australian Government) and the APFM program managed by Chemonics and ASI (USAID). In addition, there is a commitment by donors through the ARTF to support a new phase of PFMR3 with a budget of $50 million.

In that sense, there is no major financing gap for support of the proposed plan. There is however, a need to make sure that support matches priorities (including for institutional capacity building), and that support is timely and fit for purpose. In general, with the development of team based plans owned and managed by the Government, facilities of the kind that have been employed in the past, such as MBAW and SABII are no longer considered by the Government as the most effective way to manage support. Where the Government employs contracted technical assistance, we would prefer a pooled arrangement linking resources to performance through the 5-year plans and not ex-ante to activities or individual departments.

The Government acknowledges that this will require work from us to meet preconditions set by development partners to enable more effective support arrangements. To that end this plan sets out a framework for discussion that indicates the Government’s preference for support (see the next section below). This will form the basis for negotiation with donors with the default being donors providing their support through the ARTF.

Indicative costing of the external support required for this inaugural plan is around $25 million per year over the next 5 years or $125 million.

- A new framework for support

In line with this Government led and owned process for PFM reforms, the plan also presents a new support framework for discussion with donors. The Government understands that a goal of more flexible funding including through sector budget support and incentive based mechanisms is not something that can be done immediately. It is however a goal for the Government and so this plan presents a framework for discussion with development partners on what the preconditions for more flexible support might be and how in the longer term that support would be managed. Based around the principle of mutually agreed results and risk sharing.

The Government has the goal that this new approach might be put in place by the 2017 fiscal year with some initial donors and others joining over the next few years.

# Introduction

This paper represents the inaugural 5-year rolling plan for strengthening Afghanistan’s Public Financial Management systems. It is expected that successful implementation of the rolling plan will deliver on three classic public policy outcomes:

  - more efficient and effective public services;

  - significantly improved fiscal discipline; and

  - more strategic use of fiscal policy as a tool for development.

The development of this 5-year rolling plan for fiscal performance improvement has followed a different path from the past. The Government recognizes that it needs the support of development partners if it is to succeed, but also recognizes that for reforms to be achieved there must be a high level of ownership by the Government at all levels. Development of this plan has been a Government driven process. Directors, DGs and ultimately the Minister for Finance and the President formulated and approved the team-based plans that underpin this reform strategy. The Performance Management Team has trained teams in the use of the performance management system and facilitated discussions but ultimately the teams themselves are responsible for the content, direction and sequencing of reforms.

The first section on “A Team Based Performance Management Approach” provides a brief introduction in to the team-based performance management approach used to implement the 5-year rolling plan. It also explains why teams matter, why business plans matter and why grading performance matters.

The second section on “Team-Led Reforms – Every Team Matters” presents the case for having plans for all directorates within the Ministry of Finance and partner agencies involved in PFM reforms. This section outlines all agencies participating in this first year, as well as the expansion of the program over the next few years. It also provides a summary of the Flagship Reforms along with aspirational targets for international benchmarks.

The third section discusses Risk-Return Profiles of the activities under the plan. It discusses the expected impact of reforms and the risk of failure of the activities in the plan both in aggregate and for some key teams.

The fourth section on Staffing Priorities describes gaps in capacity and technical assistance (TA) requirements.

The fifth section covers financing requirements to help deliver successful reform.

The final section presents the Government’s Sector Budget Support Policy Framework as a (potential) core financing and performance monitoring mechanism. This framework forms the basis for discussions over the next 12 months on more effective support for PFM reforms and what preconditions will be required by development partners for them to consider targeted sector budget support.

# Afghanistan’s inaugural 5-Year Rolling plan

## A Team Based Performance Management Approach

This section briefly introduces the team-based performance management approach used to implement the 5-year rolling plan. It explains why teams matter, why business plans matter and why grading performance matters. This section describes how the performance management system works – with a focus on systems that help teams work on implementation of their reforms.

Conflict affected and fragile states are difficult operating environments. Often, blame for low levels of Government ownership and heavy reliance on technical assistance focusses on perceptions of low capacity. Afghanistan has to some extent suffered from the same issues, but the Government is committed to changes that will build the credibility of the state. One of the key mechanisms the Government is utilizing to build capacity and credibility is through team-based performance management.

Team-based performance management is at heart of the Realizing Self-Reliance agenda. Team-based Performance Management in this context is designed to:

Ensure Officials Run Ministries – not Advisors, Consultants or other stakeholders;

Improve the Quality of Spending – implementers are clear on their responsibilities and stakeholders know why, how, what and where reform and spending happens; and

Set the foundations for Donors to link financial assistance to performance - when conditions are right for a donor.

Why Team Based Performance Matters

Team based performance matters to leadership and reflects 5 core values.

We Believe That:

1. Strong Teams Deliver the Best Results

2. Every Team and Every Team Member Matters

3. Measuring, Rating and Ranking Performance Helps Teams Work Better and Deliver Better Results

4. We Must Recognize Efforts of Hard Working Teams and Help Those Teams Who Need It The Most

5. A Resilient and High Performing MoF will Help Realise a Long and Prosperous Future for Afghanistan and All Its People

By instituting team-based performance management, the Government is saying we value institutional culture as the primary determinant of performance. Moreover, we believe that managing teams is more effective than managing reform themes. Focussing on teams means direct lines of reporting and increased accountability for results. It also means important institutional enablers and support systems, like IT, internal ministry level budgeting and accounting do not slip through the cracks.

Improving performance is a strategic goal, anchored in practical activities, outputs and outcomes in the context of reforms to public financial management in Afghanistan. Key goals for performance management and for building systems under this plan are set out in Box 2 below. These are common goals for any fiscal performance improvement plan and for any capacity building plan for a Ministry of Finance and form a foundation for the Government to build on.

The Seven Goals for Performance Management:

Deliver on the Three Core Budgetary Outcomes

1. Improve efficiency and effectiveness of public services and service delivery (better education, improved health and greater confidence in government)

2. Deliver sustainable public finances by being strategic on how resources are allocated, distributed and spent (economic efficiency)

3. Strengthen fiscal discipline by doing what we say, hitting our targets, and running orderly processes

Deliver on Four Complimentary High Priority Objectives

4. Manage an improving, stable and secure economy creating jobs, increasing opportunities for all, reducing uncertainty and creating conditions for stability

5. Be more accountable to all stakeholders in the pursuit of good governance

6. Be more transparent – to different internal and external stakeholders ; 
on what the government is doing;  in a way that is relevant to stakeholders

7. Deliver continuous improvement through integrated systems of trial and error based around the integrity of the budget cycle.

While it is a central part of the plan, team-based performance management is not an end in and of itself. It is part of a broad foundation theory for positive change. The full theory is set out in the Government’s implementation strategy paper cited in the introduction.

In summary the key components are:

Conform to aid effectiveness principles for fragile states including ownership, alignment, harmonisation, managing for results, mutual accountability and the New Deal’s TRUST and FOCUS priorities for working in conflict affected and fragile states:

Follow the Basics First Approach to help prioritize and sequence PFM reform activities over time;

Target the weakest links in the budget cycle to ensure the system is self-improving;

Utilise analytical techniques regularly to assess technical and political feasibility of reform options; and

Introduce a Team-based Performance Management culture starting with integrating team-based performance management into reform program design and monitoring and evaluation systems.

It is important to base performance management around rolling plans that reflect the challenges the Government faces. The context of conflict means that reforms are not simple and will take time. Results will be uneven. By establishing 5-year plans, we can ensure high impact but achievable reforms, and that we are carefully tracking progress along the way. Every team will contribute to results, because we know that every team counts. We cannot break the cycle of dependency on external assistance if we do not fix Human Resource (HR) systems, Information Technology (IT) infrastructure and internal budget and accounting processes in government agencies.

Why a 5-Year Rolling Plan?

A “rolling plan” is a finance term for “plan which is designed to continue over a period of time and is subject to regular review and updating”. The underlying logic for 5 Year Rolling Plans within the context of fiscal performance improvement is threefold:

Improving fiscal performance takes time – reform activities are prioritized and sequenced and plans show how we tackle activities over a number of years. 5 Years is the period that covers most grant agreements and is the standard planning time horizon used in budget systems with a fully functioning system of rolling forward estimates.

Progress against plans is not uniform – completion of some planned activities is quick and to a good standard, while others take longer than expected to complete and/or achieve a sufficient level of quality. Some reform activities are contingent on the completion of other activities first. Consequently, there needs to be a routine system to adjust the plan based on progress.

The budget cycle is (or should be) a continuous improvement cycle for the public sector - hence performance frameworks need to be set within the context of the budget process / cycle. This means that: i) at the start of the fiscal year implementing agencies are clear about what is expected of them (i.e. the reform activities in the plan that can be funded); and ii) near the end of the fiscal year, performance is reviewed so that changes can be made to financial and non-financial plans as necessary.

How does it work?

The Continuous Performance Improvement Cycle

Performance grading

The implementation of the 5-year rolling Fiscal Performance Improvement Plan is a tool to achieve reforms. The Government established a small Performance Management Team (PMT) within the Macro-Fiscal Performance Department (MFPD) at the Ministry of Finance to facilitate the process. The PMT is under the direct supervision of the Minister for Finance and is responsible for:

Facilitating intensive team-based discussions that turned the PFMR-II strategy into a 5-year rolling plan based around a range of key performance indicators.

Designing and maintaining a system for monitoring progress and rating performance. The design of the system is for monitoring team performance, and training to all staff in how their performance is measured.

Facilitating semi-annual team based performance discussions and annual performance reporting to the Minister and Deputy Ministers on progress with implementation of the PFM Roadmap. Teams self-assess their own performance and the PMT will moderate and ensure independent validation of scores and facilitate discussions based on evidence.

The performance scoring approach adopted is one that scores each activity. Grading uses a standard alphanumeric system from D– meaning worst performance to A+ meaning best performance.

Grades are applied against three core performance dimensions:

timeliness – was the activity done on time or was it late;

quality – was the activity done to a high or low quality; and

effectiveness – how effectively did teams deal with problems?

Other Performance Related Ratings – TA, Impact and Risk

While the first two dimension are the most common and self-explanatory, the third dimension is the most important. Focusing on how teams manage problems while pursuing reform helps teams to understand and explain achievements. A fourth performance dimension quantifies the amount of international and national technical assistance provided in support of the reform activity.

This is tracked in order to:

Ensure that teams being run by Afghans with low or no international TA are not disadvantaged in performance ratings;

Ensure teams that are being run with low levels of national consultants are not disadvantaged; and

That the self-reliance agenda is a prominent component of the performance management system.

An assessment of the impact (or importance) and the risk of failure or difficulty of each reform activity was undertaken. Scoring rules established for both these dimension are in the implementation strategy paper noted above. For example, assessment of the impact of an activity includes its contribution to achieving: i) improvements in international benchmarks (e.g. PEFA and OBI) and/or perception indexes; ii) more efficient and effective public services; and iii) stability and legitimacy of Government.

Rating the risk of failure of an activity is in six different dimensions. This is to help deliver a more objective risk assessment rather than one based simply on opinion. These dimensions are drawn from the Diamond approach and are:

Number of organisations required – more organisations means a higher risk of failure.

The time required – the longer it takes means a higher risk of failure

Complexity and scope – the more complex an activity or the wider the scope means a higher risk of failure

Behaviour change required – the more behaviour change required the higher risk of failure. If a lot of change is required of a few people or a small amount of change of a lot people both imply a higher risk of failure.

Visibility – the more visible an activity is, or how easy it is to link it to real results, means that the risk of failure is reduced (e.g. political support makes it easier to overcome problems); and

Existing fiscal management competencies – the greater the capacity for performing fiscal management the lower the risk of failure. This dimension is a proxy for the need for technical assistance.

Ratings used are high, substantial, moderate, and low, which are all assigned numerical equivalents. Both raw scores and standardized scores, which are equivalent to the notions of relative impact and relative risk.

These two components of risk and impact are particularly important for reform programming and team-based performance management. Firstly, they allow for an objective assessment of the risk of failure of a reform option. Secondly, it allows for review of high risk and high impact activities in a way that reduces the risk of failure (e.g. by splitting the activity into phases). Thirdly, it facilitates team-based performance management by recognising that some teams are focus on more difficult and important work compared to other teams. It also provides a solid foundation to produce defendable league tables of reform performance during implementation.

Routine Performance Reviews – following the budget cycle

The Government will produce two performance reports every year. The system works within existing management systems with the PMT facilitating performance reporting on team-based plans. This will enable implementers to implement and not overburden teams with reporting while at the same time improving the amount of performance information generated across the Government. Teams are accountable for performance through various mechanisms including facilitated self-assessment, publishing of league tables ranking each team against one another and by requiring teams to explain their performance to their leadership in six monthly validation meetings.

Performance assessments will be twice per year:

In the first half of the year. To help ensure efforts are on track to deliver annual reform actions by the end of the year, but also to ensure relevance of reform activities being undertaken and validate any donor performance payments for the following year; and

Near the end of the year. To assess end-of-year progress (with time to spare to correct any major problems), but also to trigger and finalize any linked performance payments to be made in the following year, while also ensuring that the best estimates of any programmatic budget support are included in the annual budget papers.

At the end of every year, we will produce a new 5-year plan. This will involve rolling over the next year’s plan to the new current year’s plan, subject to progress made during the current year. Rolling forward some activities from the current year into next year will occur if there is insufficient progress. Review of future year activities will be in light of progress. Expectations are that some activities drop off and new activities taken on due to changing priorities.

The 2016 – 17 Performance Management Cycle

## Team-Led Reforms – Every Team Matters

The principle that every team matters is at the heart of the performance management culture the Government is trying to foster. Development agencies often make much about institutional capacity building but typically, make much more effort to support the areas considered critical to policy outcomes relative to building the foundations of local institutions. In the area of Public Financial Management, that invariably means prioritising Budget, Treasury, Revenue, and Macroeconomic policy over HR, finance, administration, IT and security. During a crisis phase such as prevailed in Afghanistan a decade ago, this is understandable. Delivery of the budget using external support was the standard. However, this is unsustainable in the longer-term and a meaningful transition has to occur at some point. Analysis shows that since 2010, progress on reforms has stalled and donors continue to lament a lack of ownership by Government officials.

In reality, the capacity of the Government in a number of core functions (in the MOF and other ministries) such as HR, finance and administration remains low, and (all but) ignored by successive reform programs. In order for the Government to manage the country’s finances sustainably, we must address this situation.

In purely practical terms, if the Government wants donors to provide flexible support, we must show the donors that we can manage their money without increasing fiduciary risks. As a benchmark, the Government cannot expect donors to provide sector budget support or performance incentives if the fiduciary risks are higher than putting their money into a World Bank Administered trust fund.

Similarly, the Government must be accountable to its own people for managing an increased share of domestic revenue generated for the budget by improving its budget planning and reporting on how it invests taxpayers’ money.

Administrative units – or teams - are the machinery of Government institutions that are responsible for delivering results. Without a stronger corporate backbone and consistent business planning at the team level, this ambitious reform agenda for the budget cannot succeed, and Afghanistan cannot break the cycle of dependency on external assistance.

### Teams within Teams – Participating Agencies

This 5-year plan starts all agencies within the Ministry of Finance and two external entities (AEITI and the NPA). There are currently 19 Directorate Generals involved including 63 Directorates (see Table 1).

Current Participating Agencies

| 1.0 Office of the Minister | 8.0 Property Department |
| --- | --- |
| 1.1 OoM: Comms and Public Relations Directorate | 8.1 PD: Provincial Property Directorate |
| 1.2 OoM: Correspondence Office | 8.2 PD: Registration and Resolution Directorate |
| 1.3 OoM: Legal Advisors | 8.3 PD: Capital Properties (Kabul) Directorate |
| 1.4 OoM: Archive Office | 9.0 Human Resources Department |
| 1.5 OoM: Translation Board | 9.1 HRD: Training & Development |
| 1.6 OoM: Protocol Office | 9.2 HRD: Recruitment Development |
| 1.7 OoM: Non-Allocated Advisor Pool | 9.3 HRD: Organizational Development |
| 1.8 OoM: Office of the Chief of Staff | 9.4 HRD: Performance Appraisal & Record Keeping |
| 2.0 Customs Department | 9.5 HRD: Employee Relations |
| 2.1 CD: Customs Support and Development | 10.0 Insurance Department |
| 2.2 CD: Law Enforcement | 10.1 ID: Insurance Affairs |
| 2.3 CD: Customs Technical Affairs | 11.0 Internal Audit Department |
| 2.4 CD: Operations | 11.1 IAD: Office of the DG |
| 2.5 CD: Internal Audit Unit | 11.2 IAD: Compliance IT Audit & Fraud Investigation |
| 3.0 Revenues Department | 11.3 IAD: Budget and Treasury Audit |
| 3.1 RD: Office of the DG (Revenue) | 11.4 IAD: Customs and Revenue Audit |
| 3.2 RD: Large Taxpayers Office | 11.5 IAD: Budgetary Audit and Capacity Development |
| 3.3 RD: Medium Taxpayers Office | 12.0 Programs Implementation and Coordination General Directorate |
| 3.4 RD: Small Taxpayers Office | 12.1 PICGD: Directorate for Coordination of National Priority Programs |
| 3.5 RD: Appeals | 12.2 PICGD: Directorate for Policy Research |
| 3.6 RD: Legal | 13.0 Monitoring, Analysis and Reporting General Directorate |
| 3.7 RD: Non-Tax Revenue | 13.1 MARGD: Directorate of Program Monitoring |
| 3.8 RD: Technical and Provincial Liaison | 13.2 MARGD: Directorate for Analysis and Reporting |
| 3.9 RD: Revenue Services and Support | 14.0 Reform Implementation Management Unit |
| 4.0 Treasury Department | 14.1 RIMU |
| 4.1 TD: Treasury Systems Development | 15.0 Revenue Planning Department |
| 4.2 TD: Accounting | 15.1 RPD: Revenue Analysis and Forecasting |
| 4.3 TD: Payments | 15.2 RPD: Monitoring and Evaluation of Revenue Targets |
| 5.0 Budget Department | 16.0 Macro-Fiscal Performance Department |
| 5.1 BD: Budget Execution | 16.1 MFPD: Fiscal Directorate |
| 5.2 BD: Budget Policy | 16.2 MFPD: Macroeconomic Unit |
| 6.0 Admin Department | 16.3 MFPD: Admin and Reporting Unit |
| 6.1 AD: Procurement and General Services | 16.4 MFPD: Performance Management Team |
| 6.2 AD: Finance and Accounting | 17.0 Aid Management Directorate (Not DG) |
| 6.3 AD: IT | 17.1 ADM: Aid Management |
| 6.4 AD: MoF Project Implementation Unit | 18.0 Office of the President |
| 6.5 AD: Auctions and Disposals Unit | 18.1 National Procurement Authority (NPA) |
| 6.6 AD: Gender Unit | 19.0 Other Partner Agencies |
| 7.0 SOE Department | 19.1 AEITI Secretariat |
| 7.1 SD: Policy & Coordination |  |
| 7.2 SD: Financial Monitoring SoCs |  |
| 7.3 SD: Financial Monitoring SoEs |  |
| 7.4 SD: Divesture of State Profitable Entities and Establishment of New State-Owned Enterprises and Corporations |  |

The Government plans to expand the reach of the team-based performance management system over time. Priority partner agencies in this first phase of reforms are those central agencies responsible for systems related to Public Financial Management. In addition, as the system evolves, we will incorporate key agencies and line ministries, focussing on their corporate, budget and finance sections.

Initial discussions with key agencies have already started. The Government expects that the Central Statistics Office (CSO), Supreme Audit Office (SAO), Ministry of Agriculture Irrigation and Livestock (MAIL), Ministry of Interior, the Independent Directorate of Local Governance (IDLG), and the Afghanistan Independent Land Authority (ARAZI or AILA) will be included in the 2017 5-year Rolling Plan.

### The Flagship Reforms – Taking on the Big Challenges

The complexity and enormity of this reform effort is evident in the team level 5-year rolling plans attached to this paper. Included in this inaugural plan are 19 General Directorates and 63 Directorates. Each Directorate has identified around 10 to 12 activities for monitoring and assessment. Meaning the Government is implementing around 700 activities many of which have sub-activities. This is just the core agencies responsible for the PFM system, and does not yet include line ministries who actually spend the national budget, which we will phase into the performance management system beginning in 2017.

This reflects a reality that is often lost when reforms are “projectised” and the focus is solely on strategic level outcomes. Government is big and complicated. Despite this complexity, it is incumbent on the Government to provide a coherent narrative on what this all means.

This plan forms the basis of the PFM reforms outlined by the President and the Minister for Finance to the International Community in Kabul in late 2015. This plan will be the scorecard for when the Government next reports to its development partners later this year.

To this end this next section summarises the flagship reforms under three headings:

  - Reforms to improve the performance of Government investments, leading to better economic outcomes

  - Reforms to ensure the budget is more accurate, transparent and free of corruption; and

  - Reforms to build the capacity of the state to manage reforms, beginning with investments in things like HR, administration, finance, IT and communications within the MOF.

The flagship reforms in the plan begin with improving the performance of investments leading to better economic outcomes. This reflects in a number of key areas.

Firstly, the government has established a new Macro-Fiscal Performance Department (MFPD) reporting directly to the Minister for Finance. This is significant as this is the technical part of Government responsible for bringing revenue and expenditure estimates together and, based on economic parameters, presenting the fiscal outlook to the Cabinet. The MFPD plan focusses on making fiscal space analysis the context for Cabinet consideration of the priorities for the annual budget. It will also help underpin the creation of credible forward estimates for the budget. A statement of national priorities by the Government based on improved macro and fiscal analysis will lay the foundation for linking policy and budgets.

Secondly, the Government has established the Programs Implementation and Coordination General Directorate to support the functions of the Development Councils whose primary function is to guide national priorities. This is in effect a Cabinet Secretariat role and their plan focusses on setting up robust procedures for managing the business of the councils. This allows the Directorate General of Budget to direct budget submissions towards national priorities with a clear understanding of the fiscal space available for Government investment.

This improvement in the policy setting process at the start of the annual budget cycle will reinforce a range of measures to ensure the accuracy, transparency and robustness of the budget. This will begin with efforts to introduce more systematic, accurate and rule-based costing of budget proposals piloting new approaches in the MOF before rolling them out to other Ministries. There will also be trials of reforms to commitment controls to ensure the use of allotments is for their intended purpose. With improved forecasting and the establishment of rolling forward estimates, we will see the elimination of the systematic over estimation of both revenue and expenditure that has been a feature of the national budget over recent years. This is a key reform area if Afghanistan is to reach its aspirational targets under international benchmarks for good public financial management.

Treasury will make very large investments in the Afghanistan Financial Management System (AFMIS) to bed in important improvements to the management of expenditure. An upgraded AFMIS will link contract and procurement information to Treasury functions. This will combine with improved cash management and commitment controls to remove most of the points of discretion in the system that allow for corruption. The National Procurement Authority (NPA) will work with Treasury to ensure no payments to any project that has not met Government procurement standards. Similarly, contractors will receive no milestone payments unless the contract and milestones are on the system.

Budget reporting remains an area in need of significant improvement. As noted in the President’s PFM Assessment and in PEFA scores, an accurate comparison of the budget to the end of year financial accounts is not possible with current structures and systems. The Government intends to move to a consolidated national budget over time with one currency and one accounting standard. The Government will introduce ministerial budget statements at the beginning of the fiscal year and annual reports that compare budgets to actuals. The MoF will pilot these reforms, which will then roll out to all line Ministries over the next few years. This will not replace internal and external audit with the 2016 plan focussed on strengthening internal audit to meet international standards and building capacity for audit.

Revenue is an area that has already been a key focus for the Government, with significant improvements already achieved. This plan shows strong intent in revenue and customs to increase revenue. The focus is on doing the basics first, expanding the reach of the revenue authorities and improving compliance. Policy measures will remain under consideration but the reach and capacity of the revenue and customs departments to administer the current system is the priority. This will be a key area for donor support, particularly in expanding the reach of the Government into the districts.

None of this will be possible unless the Government can improve its institutional capacity to manage the national budget. This plan contains significant measures to improve HR, IT, administration and especially internal budget and financial management processes. The Government will begin with the MoF and add in key line ministries over the next year or two. These reforms aim to reduce fiduciary risks and improve the performance of the Government. A good example is the policy of moving away from externally contracted staff towards more use of CBR and making sure that all core positions are Tashkeel. TA will be still be needed but it will now be restricted to a small number of genuine skills gaps.

This policy reflects the Government’s decision not to seek to extend or replace the UNDP supported MBAW or the UK supported SABII in the short term. While these programs have made a significant contribution to the Government’s capacity, the Government’s focus is on putting in place long-term business plans, with sustainable staffing profiles with officials in all key positions. With this done, we will targeted external support to meet the Government’s needs.

MoF will incorporate the detailed anti-corruption, currently under Cabinet consideration, into the plan at the mid-year assessment.

Flagship Reforms of the Teams

| DG | Flagship Reforms |
| --- | --- |
| 1.0 Office of the Minister | Delivering effective management through the leadership group |
|  | Establishment of a Legal Board |
|  | Setting up an electronic archiving system to support management |
| 2.0 Customs Department | Comprehensive program of legislative, system and administrative reforms. |
|  | Targeting key corruption areas including valuations, clearance times, reconciliation of assessments, payments and transfers, and customs debt collection performance |
| 3.0 Revenues Department | Comprehensive program of legislative, system and administrative reforms including expanding the reach of the tax system to the provinces. |
|  | Targeting key corruption areas including reconciliation of tax assessments, payments and transfers, and debt collection performance. |
|  | Other key work programs: i) IT/Sigtas development; ii) integration of an anti-corruption strategy including developing systems to mitigate risk of inappropriate relationships between tax assessor and tax payer; iii) developing a fair appeals system; iv) tax legislation strengthening program; v) developing options for broadening of the tax base - Vat is back. |
| 4.0 Treasury Department | Introduction of web-based AFMIS with much more powerful functions - improved reach, purchasing, commitment controls and contract management systems. Zero balance sweeping. Sub-Accounts trials. Stronger payroll controls and linkages with HR systems |
| 5.0 Budget Department | Rolling Forward Estimates for Policy Linked Budgets, Single Currency, Integrated Budget, Piloting new systems commitment control systems within MoF (allotments). Program budgeting s.t. setting these pre-conditions. |
| 6.0 Admin Department | Work program to deliver better budgeting, accounting, procurement and IT services to MoF. |
|  | DG level budgets in 2017. Single IT network and website, and secure email. |
| 7.0 SOE Department | Will be assessing fiscal risk posed by SoEs and SoCs and taking on new supervision function of state-owned Banks (fiscal risk only) |
| 8.0 Property Department | Solid program to continually double revenue over three years. Dealing with the problems of former Banks (Agricultural, Industrial, Mortgage and Construction Banks) - |
| 9.0 Human Resources Department | Exploring PFM competency testing. Merit based devolved recruitment. Working with Treasury to pilot new systems for HR and Payroll controls. |
| 10.0 Insurance Department | Seeking to develop Islamic insurance and micro-insurance |
| 11.0 Internal Audit Department | Implementation of IIA Standards. Risk based auditing and introduction of follow-up procedures. |
| 12.0 Programs Implementation and Coordination General Directorate | Secretariat to the Development Councils - rules and procedures |
| 13.0 Monitoring, Analysis and Reporting General Directorate | Monitoring and reporting on national programs. |
| 14.0 RIMU | Servicing the World Bank - Structural issues to be reviewed including with Admin PIU |
| 15.0 Revenue Planning Department | Improving revenue forecasting enabling provincial level targets. Surveys of total tax payers. |
| 16.0 Macro-Fiscal Performance Department | Working with Budget and the policy linked budgeting. Rolling Forward Estimates, New Policy focus and Fiscal Space. And PMT |
| 17.1 ADM: Aid Management | Working with Donors, MFPD, Budget and Treasury to deliver timely and quality consolidated budgets and accounts |
| 18.1 NPA: National Procurement Authority | Comprehensive reform taking on the big issues. Medium term plan to decentralize. E-Procurement including contract management (working with Treasury) |
| 19.1 AEITI Secretariat | Working with government agencies to help revealed weakness in revenue and contract management – helping to close loopholes including closing revenue leakages of c$1 b pa. |

### Aspirational Targets – Our Guides

An initial set of aspirational (guiding) targets have been established helping to transform the PFMR-II Strategy into a rolling 5-year Fiscal Performance Improvement Plan. Fixed aspirational targets throughout the reform period ensures teams are focusing on building systems that work in the local context but also meet international standards. They will also assist donors in interpreting progress made in various areas of reform.

#### International Benchmarks

All teams have discussed an initial set of aspirational targets against international benchmarks in the context of developing their individual team’s 5-year rolling plan.  These will be further refined in the mid-year review and formally adopted by the Government by the end of this year. In this plan four international benchmarks will be used:

Public Expenditure and Financial Accountability (PEFA) framework – current version and the upgraded version under testing;

Open Budget Index;

Statistical Capacity Indicators; and

Doing Business on Tax and Customs.

Figure 3 below presents the trends in PEFA and PEFA-10 scores for Afghanistan since 2005 and the initial aspirational targets the Government is considering for the medium to long term (green columns). Between 2005 and 2008, there was good progress was in raising PEFA scores, meaning the overall quality of PFM systems has improved and the level of inherent fiduciary risks has fallen. However, from 2008 onwards, progress has plateaued. The Government is proposing achievable but ambitious targets, recognising that it is much harder to rise to the top from the middle ground than it is to rise to the middle ground from a low base. For a complete list of the initial aspirational targets for each PEFA dimension, see Attachment B: Aspirational and Guiding Targets to support Implementation of the PFMR-II.

Aspirational Targets for PEFA and PEFA-10

Each team has assigned a range of PEFA indicators to their activities. Discussion of these aspirational targets and the actions needed to achieve the targets formed part of the process for establishing the initial 5-year plans. They are included in the mid-year and annual performance assessments.

Selected Aspirational Targets for Upgraded PEFA

Aspirational targets have also been set for key indicators under the Upgraded PEFA. The upgraded PEFA introduces new fiscal management performance indicators, previously not covered by PEFA or any other generally excepted diagnostic. Key areas covered include: i) public investment management; ii) public asset management; and iii) key areas related to medium term budgeting and fiscal risk management. These three previously uncovered areas are particularly relevant for Afghanistan to help overcome problems like over-budgeting, weak distribution of resources and inefficient spending.

Aspirational targets for the Open Budget Index (OBI) – for every one of the 125 OBI questions and every one of the eighteen (18) OBI sub-groupings. This is a step to meet eligibility conditions under the Open Government Partnership (OGP). Aspirational targets under OBI are required to strengthen the Government’s capacity to defend its performance with ratings agencies.

Figure 5 below reveals OBI trends since 2008 for Afghanistan and presents the proposed aspirational OBI targets in green columns. For a complete list of the aspirational targets for each OBI, question and selected indicators under the upgraded PEFA see Attachment B: Aspirational and Guiding Targets to support Implementation of the PFMR-II.

Aspirational Targets for Open Budget Index

OBI groupings assigned to teams can be seen Figure 5, along with relevant questions for the MoF and other agencies / ministries. These targets and the actions needed to achieve the targets are part of the rolling over of - and any adjustments to - the 5-year plans in 2017.

Figure 6 below presents aspirational targets for Statistical Capacities along with trends in Statistical Capacity Indicators since 2005. All three areas are targets for improvement. Further work with the statistics agencies and line ministries on performance management will enable prioritization of missing areas in statistical capacities. For a complete list of the aspirational targets for each statistical capacity indictor theme question see Attachment B: Aspirational and Guiding Targets to support Implementation of the PFMR-II.

Aspirational Targets for Statistical Capacities

Doing Business: Proposed Aspirational Ranks (100 Best)

Two components of Doing Business are believed to be particularly relevant as potential aspirational targets – those areas that assess how hard (or how easy) it is to do business because of Tax and Customs Systems. The trends and proposed targets for these two areas are in Figure 7 below. Table 3 also gives the underlying data that determines scores and Distances to Frontiers (DTF), where 100 is best and 0 is worst.

Setting targets for tax in a country like Afghanistan has its difficulties, since low tax is good for business by “Doing Business” metrics and good for attracting foreign investors. However, it is also bad for revenue generation and more importantly potentially bad for accountability systems in a country if tax is too low. Target levels were reviewed against other countries and it was felt the tax system in Afghanistan could be more onerous on business as it is rated as very lenient- arguably too lenient - with zero scores against profit and labour taxes. In addition, the Presidential Assessment (GoIRA, 2015) revealed very low levels of tax take relative to other comparable countries. This implies that widening and deepening the tax base through better reach, increased enforcement and new taxes are all viable reforms and policy positions. Reviews of Tax targets will be included in the mid-year and annual performance assessments.

Trends in Tax Collection – Selected Comparators

Source: WDI

For Customs, initial aspirational targets to reduce times and costs to export and import are proposed against current Doing Business methodologies (see Table 3). While “doing business” changes its methodologies generally every year, making it difficult to set medium term targets, aspirational and general targets are still possible. As in the case of Customs, reducing the cost and time taken to import and export are important goals. The problems emerge, when the international goal posts for calculation keep moving.

Table 5 provides the status of custom clearance times and documents with the target reduction in time taken. We chose Pakistan, India and Iran as comparators for benchmarking purposes – they are particularly relevant as core trading partners. A review of Customs targets will be included in the mid-year and annual performance assessments.

DB Taxes & Customs: Proposed Aspirational Targets (100 Best)

| Year/DB Component und MoF Influence |  | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | Asp Target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ease of Doing Business Rank |  |  |  |  |  |  |  |  |
| Paying Taxes | DTF | 74.14 | 74.14 | 74.14 | 74.14 | 74.39 | 74.39 | 65 |
|  | # Payments (number per year) | # 20 | # 20 | # 20 | # 20 | # 20 | # 20 | # 12-33 |
|  | # Time (hours per year) | # 275 | # 275 | # 275 | # 275 | # 275 | # 275 | # 243 |
|  | # Profit tax (%) | # .. | # .. | # .. | # .. | # 0 | # 0 | # 25.3 |
|  | # Labor tax and contributions (%) | # .. | # .. | # .. | # .. | # 0 | # 0 | # 20.7 |
|  | # Other taxes (%) | # .. | # .. | # .. | # .. | # 35.8 | # 35.8 | # 15.7 |
|  | # Total tax rate (% profit) | # 36.3 | # 36.3 | # 36.3 | # 36.3 | # 35.8 | # 35.8 | # 61.7 |
| Trading Across Borders | DTF | 17.71 | 11.26 | 14.1 | 16.97 | 10.76 | 9.21 | 45 |
|  | # Documents to export (number) | # 10 | # 10 | # 10 | # 10 | # 10 | # 10 | # 7 |
|  | # Time to export (days) | # 74 | # 74 | # 74 | # 74 | # 81 | # 86 | # 17.1 |
|  | # Cost to export (US$ per container) | # 3,030.00 | # 3,545.00 | # 3,545.00 | # 3,545.00 | # 4,645.00 | # 5,045.00 | # 1332 |
|  | # Documents to import (number) | # 4,033.50 | # 4,820.60 | # 4,404.90 | # 3,984.10 | # 4,820.30 | # 5,045.00 | # 1332 |
|  | # Time to import (days) | # 10 | # 10 | # 10 | # 10 | # 10 | # 10 | # 10 |
|  | # Cost to import (US$ per container) | # 77 | # 77 | # 77 | # 77 | # 85 | # 91 | # 21.1 |

Nb: Aspirational targets based on reaching levels equivalent to neighbours

Tax Payments and Times

| Tax or mandatory contribution | Payments (number) | Time (hours) | Statutory tax rate | Tax base | Total tax rate (% profit) |
| --- | --- | --- | --- | --- | --- |
| Sales tax | 4 | 78 | 2% | sales | 35.35 |
| Road toll tax | 1 |  | AFN 7,500 | fixed fee | 0.4 |
| Vehicle registration tax | 1 |  |  | various | 0 |
| Fuel tax | 1 |  |  | in fuel price | 0 |
| Personal income tax | 12 | 120 |  | income | 0 |
| Corporate income tax | 1 | 77 | 20% | profit | 0 |

Customs Documents and Times

| Import documents |  |  |
| --- | --- | --- |
| Bill of lading |  |  |
| Certificate of origin |  |  |
| Clean inspection report of findings |  |  |
| Commercial invoice |  |  |
| Customs export declaration |  |  |
| Customs transit document |  |  |
| Insurance certificate |  |  |
| NOC/ Transit permit |  |  |
| Packing list |  |  |
| Terminal handling receipts |  |  |
| Nature of Import Procedures | Duration (days) | US$ Cost |
| Documents preparation | 49 | 680 |
| Customs clearance and inspections | 7 | 300 |
| Ports and terminal handling | 5 | 200 |
| Inland transportation and handling | 30 | 4,500 |
| Totals | 91 | 5,68 |
| Export documents |  |  |
| Bill of lading |  |  |
| Certificate of origin |  |  |
| Clean inspection report of findings |  |  |
| Commercial invoice |  |  |
| Customs export declaration |  |  |
| Customs transit document |  |  |
| Insurance certificate |  |  |
| NOC/ Transit permit |  |  |
| Packing list |  |  |
| Terminal handling receipts |  |  |
| Nature of Export Procedures | Duration (days) | US$ Cost |
| Documents preparation | 49 | 680 |
| Customs clearance and inspections | 7 | 300 |
| Ports and terminal handling | 5 | 200 |
| Inland transportation and handling | 30 | 4,500 |
| Totals | 91 | 5,680 |

Custom-designed medium term targets are in place for certain teams. These are reflected in the individual teams’ 5-year plans and have annualised targets as well as medium-term expected outcomes.

#### Reform Risk-Return Profiles – Calculated Risk Taking

This 5-year plan takes on the biggest challenges - but this risk of failure is high. Comprehensive documentation of systemic weaknesses in public financial management are including in PEFA assessments and the Presidential Fiduciary Risk Assessment. This 5-year plan tackles these weaknesses. Moreover, ownership of the proposed reforms is high as teams developed their own plans and ultimately agreed to the content and sequencing of activities. Through the planning process, the impacts and risks were analysed using the Diamond approach (see footnote 7).

This approach helps to manage the risk of failure, making sure that the Government delivers on reforms. The two biggest flagship areas of whole-of-Government systemic reform are in the areas of Budget and Treasury.

Key performance indicators for the budget have shown little improvement under PEFA at an average D+ (see Figure 9). The budget is too inaccurate to be a useful policy tool for government. Budget officials spend most of their time overseeing the contracts of line agencies (through the budget allotment process) rather than focusing on delivering aggregate fiscal discipline (accurate budgets). This is most evident in the lack of a robust new policy costing process, undermining development of robust forward estimates. The budget classification and reporting system is also still too opaque and is not sufficiently comparable with the higher standard accounting classification system.

The budget preparation system has in the past, essentially been a project bid aggregation system. A strong system of fiscal policy and strategy has not underpinned the budget. The budget has in-effect been short sighted, compromising the ability of the budget process to be a tool for driving and achieving Government policy. The budget has also failed to set the foundations for a culture of reporting on performance, where minsters are accountable for their promises and for results. The lack of a consolidated national budget that is comparable to consolidated financial accounts means that the continuous improvement function of the budget cycle is broken. The plan sets out to address all these problems. However, it will take time, with the risk of failure and false starts being high. The plan targets that over the next 5  years these performance scores related to budget planning execution and reporting will improve from the current D+ average towards the aspirational target of B+.

Budget and Treasury: Solving Systemic Problems

Treasury functions are performing much better against international standards with an average score of B, but there are challenges to overcome (see Figure 9). Weak budget systems – classification, reporting and donor data – delivering weak comparability of budgets and accounts, also undermine Treasury’s performance scores. The big reform action articulated by Treasury in its 5-year plan involves significant strengthening of the Afghanistan Financial Management Information System (AFMIS). AFMIS in its current form has performed basic cash management functions reasonably well, but needs a significant upgrade to integrate a number of functions into the system, such as contract management and procurement.

Treasury in close partnership with the National Procurement Agency are planning to introduce advanced functionalities to core IT and accounting systems. Highlights include:

  - purchasing – so that basic contract information can be collected;

  - improved commitment controls – so that cash is managed well;

  - procurement – so that much more procurement information is linked to the broader system;

  - contract management – so that all contracts and contract milestones are on the system; and

  - establishing a true Treasury Single Account (based around sub-accounts).

These systems will take time to implement, but the impact if successful will be enormous. No obligations created, and no payments made, without all fiscal intelligence data being on the system. Such a system will prevent against, detect and gather forensic level evidence of corruption and mismanagement in a much more powerful way.

Risk-Return Profiles of team’s reform plans reveal that the proposed reforms target impactful and important work – but at a high risk of failure. Considerable effort occurred during the planning process to reduce the risk of failure by phasing in reforms, or redesigning proposed solutions to include pilots. Aggregate risk return profiles are presented for all teams (see Figure 10) and individual risk return profiles for the 5 key teams of Budget, Macro-Fiscal, Aid Management, Treasury and Admin and Finance are also presented separately (see Figure 12 and Figure 14).

Risk-Return (performance and TA) Space

Raw Risk and Raw Impact                         Relative Risk and Relative Impact

Frequency of Risk Impact Dimensions

|  | ## Impact | ## Scope & complexity of reform | ## Degree of behaviour change | ## No. of organisations | ## Time required | ## Visibility of reform impact | ## PFM Competency |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ## Low | ## 23 | ## 49 | ## 102 | ## 26 | ## 65 | ## 80 | ## 102 |
| ## Moderate | ## 90 | ## 208 | ## 155 | ## 170 | ## 152 | ## 151 | ## 299 |
| # Substantial | # 180 | # 99 | # 95 | # 157 | # 76 | # 93 | # 106 |
| High | 334 | 271 | 275 | 275 | 334 | 303 | 120 |
| Total | 627 | 627 | 627 | 628 | 627 | 627 | 627 |
| Shares |  |  |  |  |  |  |  |
| Low | # 4% | # 8% | # 16% | # 4% | # 10% | # 13% | # 16% |
| Moderate | # 14% | # 33% | # 25% | # 27% | # 24% | # 24% | # 48% |
| Substantial | # 29% | # 16% | # 15% | # 25% | # 12% | # 15% | # 17% |
| High | # 53% | # 43% | # 44% | # 44% | # 53% | # 48% | # 19% |

Reform efforts will require constant work. Fifty six percent (52%) of activities will take twelve months or more to complete starting in 2016, which could lead to significant delays in future reforms if activities roll over from this year to next year (see Figure 11).

Reform requires much better cooperation amongst teams. Forty two per cent (37%) of activities require coordination with more than 14 organisations, and Sixty one per cent (61%) requiring 6 more organisations (see Figure 11).

Time Required and Coordination Requirements of Activities

A strong office of the Minster for Finance is crucial as all roads lead to the Minister’s Office. Around sixty five percent (74%) of all organisational dependencies identified involve the Minister’s Office.

Risk-Return (& TA) Space Selected PFM Reform Driving Teams

Revenue Generating Agencies: Risk-Return Space

Admin and Finance: Risk-Return (performance and TA) Space

Figure 12 and Figure 13reveals High Risk High Return Reform profiles for activities by Budget, MFPD, Aid Management, Treasury and the revenue agencies. This is a good signal that teams are willing to tackle the hard issues, but will need monitoring in semi-annual assessments to make sure there is progress, and major reforms are not lagging behind.

Similarly, a High Risk High Return Reform profile for activities in getting MoF corporate services up to standard is also evident. This in part represents the low base that MoF is starting from but progress is crucial in MoF building the moral authority to push PFM reforms to line ministries and donors (see Figure 14).

## Staffing Priorities – Technical Assistance Gaps

The detailed 5 year plans attached to this paper reveal that much of the reform agenda is about actions being taken by teams, or in other words, by people. Teams identified technical assistance gaps across the board using a consistent methodology focussed on the underlying policy of moving away from external assistance towards self-reliance. In contrast to previous designs of projects to assist the Government, the focus is on individual actions rather than thematic areas and how much of the workload borne by either national or international TA.

The distinction between national and international TA is important as there has been a gradual fall in international TA, particularly in the MoF, but national TA remains at very high levels. In some departments national TA out number Tashkeel four or five to one. By systematically identifying where the TA is, and linking it to the major actions under the reform plan, we now have a team level view of the needs. It has also helped DGs to plan for moving long-term contractors over to Tashkeel, with CBR top ups where appropriate. There is significant progress in this area already and the Government expects to see a steady move away from long-term TA and towards genuine support for skills gaps.

However, teams still require technical assistance. Teams with low or moderate levels of (PFM) competency to deliver on time and to standard manage sixty five per cent (65%) of activities.  Team level detailed 5-year plans provide a useful tool to better target TA and need activity level costings to determine activity level financing gaps.

## Financing – Gaps

Financing of this plan will also follow a different process to previous reform programs. Much of the work is core business undertaken by Government staff. As already noted, external assistance is being phased out to the maximum extent possible and many positions are being transferred to Tashkeel with CBR top ups. This reduces the need for additional external financing.

There are also some ongoing support programs, such as PFMR2 (World Bank), the Customs Reform Project (World Bank), support to the performance management system through a grant to the Institute of State Effectiveness (DFID and Australian Government) and the APFM program managed by Chemoncis and ASI (USAID). In addition, there is a commitment by donors through the ARTF to support a new phase of PFMR3 with a budget of $50 million.

In that, sense there is no major financing gap for support of the proposed plan. There is however, a need to make sure that support matches priorities (including institutional capacity building), and that support is timely and fit for purpose. In general, with the development of team based plans owned and managed by the Government, facilities of the kind that have been employed in the past, such as MBAW and SABII are no longer considered by the Government as the most effective way to manage support. Where the Government employs contracted technical assistance we would prefer a pooled arrangement where resources link to performance through 5 year plans and not ex-ante to proposed activities.

To that end this plan sets out a framework for discussion that indicates the Government’s preference for support (see the next section below). This will form a basis for negotiation with donors with the default being donors going through the ARTF.

Indicative costing of the external support required for this inaugural plan is as follows:

Around $10m per year for targeted national and international technical assistance /capacity building. Ideally, we would like to pool this funding rather than allocate it to specific activities. This pooled arrangement would cover all agencies except Customs who have ongoing support from the World Bank.  Agencies would cost their TA needs by activity under their 5-year plans and bid for funds. The Minister would then allocate resources based on need and performance. Appropriate third party monitoring and audit are required. One option is for the Government or donors to procure a managing contractor and/or the ARTF could contribute to this pooled arrangement.

Around $5m per for support to state institution capacity building, including for travel, training, scholarships, legal advice and incentives.

Around $2m per year for IT infrastructure work. This would include building an intranet, email, HR, payroll and finance systems that would reach the entire Ministry of Finance. This could be through ARTF or through direct support.

Around $2m per year for upgrades to AFMIS. This would be through the ARTF.

$5m per year for Customs and Revenue, including for upgrades to systems and institutional capacity building.

$1m per year for 3 years for managing the performance management system.  DFID and the Australian Government through a grant to the Institute of State Effectiveness are currently supporting this initiative.

The indicative costing for external support totals around $25 million per year for the next 5 years. This allows for current activities proposed in 2016 and the expansion of the performance management system to include key agencies and line ministries from 2017. As already noted there is already around $80 million in commitments from donors leaving a financing gap of around $45 million.

Medium Term Resourcing Allocations – Economic & Function (US$)

| Item | 1395/2016 | 1396/2017 | 1397/2018 | 1398/2019 | 1399/2020 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Emp. Compensation | 600,000 | 848,000 | 1,123,600 | 1,191,016 | 1,262,477 | 5,025,093 |
| TA Compensation | 6,248,500 | 8,831,213 | 11,701,358 | 12,403,439 | 13,147,645 | 52,332,156 |
| Goods &Services | 8,748,260 | 12,364,207 | 16,382,575 | 17,365,529 | 18,407,461 | 73,268,033 |
| Capital | 4,389,940 | 6,204,449 | 8,220,894 | 8,714,148 | 9,236,997 | 36,766,428 |
| Unallocated |  | 2,968,000 | 6,741,600 | 8,575,315 | 10,604,806 | 28,889,722 |
| Total Excl. Unallocated | 19,986,700 | 28,247,869 | 37,428,427 | 39,674,132 | 42,054,580 | 167,391,709 |
| Grand Total | 19,986,700 | 31,215,869 | 44,170,027 | 48,249,448 | 52,659,387 | 196,281,431 |
| TA Total | 14,946,700 | 21,124,669 | 27,990,187 | 29,669,598 | 31,449,774 | 125,180,928 |
| Function and function Groups |  |  |  |  |  |  |
| # General Public Services | # 19,521,950 | # 28,863,023 | # 38,805,305 | # 41,610,030 | # 44,611,622 | # 173,411,930 |
| # Defence | # - | # - | # 449,440 | # 476,406 | # 504,991 | # 1,430,837 |
| # Public Order and Safety | # 264,000 | # 1,221,120 | # 1,393,264 | # 1,476,860 | # 2,070,462 | # 6,425,706 |
| # Economic Affairs | # 200,750 | # 707,727 | # 1,724,258 | # 2,304,120 | # 2,442,367 | # 7,379,221 |
| # Environmental Protection | # - | # - | # - | # - | # 504,991 | # 504,991 |
| # Housing and Community Development | # - | # 424,000 | # 449,440 | # 952,813 | # 1,009,982 | # 2,836,234 |
| # Health | # - | # - | # 449,440 | # 476,406 | # 504,991 | # 1,430,837 |
| # Recreation, Culture, Religion | # - | # - | # - | # - | # - | # - |
| # Education | # - | # - | # 449,440 | # 476,406 | # 504,991 | # 1,430,837 |
| # Social Protection | # - | # - | # 449,440 | # 476,406 | # 504,991 | # 1,430,837 |

Activity Based Costing (ABC) was undertaken. They include costs against a range of unit costs for technical assistance, security, IT works and other expenditures noted above. Costings also include expansion of the reach of the program to line ministries over the next few years. These were included in unallocated component reflecting that there were no activities to cost at this stage – only indicative allocations for admin and finance functions within line agencies. Costs by Fund source type (e.g. ARTF, USAID etc) are also included.

Fiscal Performance Improvement Costs (Shares & US$)

Overall cost estimates are almost $200m over 5 years, of which around $50m is for compensating consultants, $75m for goods and services (see Table 7). Most of the allocations ($173m) is for fiscal and financial affairs, though service delivery functions through the expanded reach into line ministries. Estimates include allocations at the administrative unit level (see Table 8).  For detailed cost estimates, see Attachment E: Costings and Resource Allocations.

Medium Term Resourcing Costings – by Administrative Unit (US$)

| Administrative Unit | Emp. Compensation | TA Compensation | G&S | Capital | Grand Total |
| --- | --- | --- | --- | --- | --- |
| 1.0 Office of the Minister | - | 1,260,417 | 1,462,083 | 250,417 | 2,972,917 |
| 2.0 Customs Department | - | 1,183,333 | 1,372,667 | 2,047,333 | 4,603,333 |
| 3.0 Revenues Department | - | 2,006,250 | 2,327,250 | 1,080,250 | 5,413,750 |
| 4.0 Treasury Department | - | 625,000 | 1,225,000 | 1,525,000 | 3,375,000 |
| 5.0 Budget Department | - | 645,833 | 749,167 | 25,833 | 1,420,833 |
| 6.0 Admin Department | - | 931,250 | 1,080,250 | 2,037,250 | 4,048,750 |
| 7.0 SOE Department | - | 402,083 | 466,417 | 16,083 | 884,583 |
| 8.0 Property Department | - | 522,500 | 606,100 | 20,900 | 1,149,500 |
| 9.0 Human Resources Department | 1,000,000 | 133,333 | 2,154,667 | 5,333 | 3,293,333 |
| 10.0 Insurance Department | - | 110,417 | 128,083 | 4,417 | 242,917 |
| 11.0 Internal Audit Department | - | 831,250 | 964,250 | 33,250 | 1,828,750 |
| 12.0 Programs Implementation and Coordination General Directorate | - | 125,000 | 145,000 | 5,000 | 275,000 |
| 13.0 Monitoring, Analysis and Reporting General Directorate | - | 50,000 | 58,000 | 2,000 | 110,000 |
| 14.0 Reform Implementation Management Unit (RIMU) | - | 50,000 | 58,000 | 2,000 | 110,000 |
| 15.0 Revenue Planning Department | - | 425,000 | 493,000 | 17,000 | 935,000 |
| 16.0 Macro-Fiscal Performance Department | - | 675,000 | 783,000 | 227,000 | 1,685,000 |
| 17.0 Aid Management Directorate | - | 220,833 | 256,167 | 8,833 | 485,833 |
| 18.0 Office of the President | - | 175,000 | 203,000 | 7,000 | 385,000 |
| 19.0 Other Partner Agencies | - | 41,667 | 48,333 | 1,667 | 91,667 |
| Grand Total (excl. Unallocated) | 1,000,000 | 10,414,167 | 14,580,433 | 7,316,567 | 99,236,833 |

## Government’s Sector Budget Support Policy Framework

The purpose of this section is to provide an outline of a proposal by the Government to establish a framework to support implementation of the Public Financial Management Roadmap II. This PFMRII Program Budget Support Framework (the Framework) forms a part of the Government’s broader foreign assistance and aid management policy. This section provides a short summary of key areas for the Government and development partners to discuss with the view to securing in-principle agreements. For details, see Attachment D.

The Government’s goal is to secure flexible arrangements, through targeted, sector budget support, based on mutually agreed results and sharing of risk. As already noted in this plan, the Government has much work to do in order to make that possible, but this proposal is a first step to establishing the preconditions that must be in place.

While the precise preconditions will need to be negotiated, and validated by independent assessment, they can be broadly summarized in the following five areas:

- Macroeconomic stability;

- A strategy for reform;

- Budget transparency;

- Political Commitment; and

- Risk Management.

The partnership principles developed by the g7+ and set out in the New Deal provide a good basis for partnerships between the Government and donors:

FOCUS on supporting inclusive country-led and country-owned transitions out of fragility (especially support for one vision, one plan, political dialogue and leadership); and

TRUST (Transparency, Risk-sharing, Use and strengthening country systems, Strengthening capacities and Timely and predictable aid) by providing aid and managing resources more effectively and aligning these resources for results.

The Government and development partners need to reach agreement on the design elements of a budget support arrangement.  Including the timeframe, the nature of support, program structures, conditions for support and joint monitoring arrangements. Once reached, these agreements could form the basis of more formal financing instruments (grant agreements) made with individual development partners who wish to participate in the budget support arrangements for the PFMRII.

Work needs to start now. If the Government and the development partners want to pursue a targeted sector or program budget support framework following the broad outline at Attachment D, there is a lot of work to do. The preconditions for such an arrangement are not in place. There needs to be a joint design process to determine each of the elements listed above.

As this plan demonstrates, the Government has thought about how this type of arrangement might work and considers a reasonable timeframe for achieving some credible preconditions and for establishing the necessary agreements would be the start of the 2017 / 1396 fiscal year

# Attachments

## Attachment A: 5 Year Plans

## Attachment B: Aspirational and Guiding Targets to support Implementation of the PFMR-II

Aspirational PEFA Targets

|  | Indicator | 2005R | 2008R | 2013 | Aspirational Target |
| --- | --- | --- | --- | --- | --- |
|  | A. PFM-OUT-TURNS: Credibility of the budget |  |  |  |  |  |
| PI-1 | Aggregate expenditure out-turn compared to original approved budget | D | D | C | B |  |
|  | # (i) The difference between actual primary [sector] expenditure and the originally budgeted primary expenditure (i.e. excluding debt service charges, but also excluding externally financed project expenditure). | # D | # D | # C | # B |  |
| PI-2 | Composition of expenditure out-turn compared to original approved budget | D | D | D+ | B+ |  |
|  | # (i) Extent of the variance in expenditure composition during the last three years, excluding contingency items | # D | # D | # D | # B |  |
|  | # (ii) The average amount of expenditure actually charged to the contingency vote over the last three years. | # D | # D | # A | # A |  |
| PI-3 | Aggregate revenue out-turn compared to original approved budget | D | D | C | A |  |
|  | # (i) Actual domestic [sector specific non-tax] revenue collection compared to domestic revenue estimates in the original, approved budget. | # D | # D | # C | # A |  |
| PI-4 | Stock and monitoring of expenditure payment arrears | D+ | D+ | C+ | A |  |
|  | # (i) Stock of expenditure payment arrears (as a % of actual total expenditure for the corresponding fiscal year) & any recent change in the stock. | # C | # C | # A | # A |  |
|  | # (ii) Availability of data for monitoring the stock of expenditure payment arrears | # D | # D | # C | # A |  |
|  | B. KEY CROSS-CUTTING ISSUES: Comprehensiveness and Transparency |  |  |  |  |  |
| PI-5 | Classification of the budget | C | C | C | A |  |
|  | # (i) The classification system used for formulation, execution and reporting of the central {SN} government’s budget [for the sector]. | # C | # C | # C | # A |  |
| PI-6 | Comprehensiveness of information included in budget documentation | C | B | C | A |  |
|  | # (i) Share of the listed information in the budget documentation most recently issued by the central {SN} government {sector Minister} | # C | # B | # C | # A |  |
| PI-7 | Extent of unreported government operations | D+ | B+ | B+ | A |  |
|  | # (i) The level of extra-budgetary expenditure (other than donor-funded projects) which is unreported i.e. not included in fiscal reports. | # B | # B | # B | # A |  |
|  | # (ii) Income /expenditure information on donor-funded {sector} projects which is included in fiscal reports. | # D | # A | # A | # A |  |
| PI-8 | Transparency of inter-governmental fiscal relations | D | D | C+ | B+ |  |
|  | # (i) Transparent and rules based systems in the horizontal allocation among SN governments of unconditional and conditional transfers from central government (both budgeted and actual allocations); | # D | # D | # C | # B |  |
|  | # (ii) Timeliness of reliable information to SN governments on their allocations from central government for the coming year; | # D | # D | # D | # B |  |
|  | # (iii) Extent to which consolidated fiscal data (at least on revenue and expenditure) is collected and reported for general government according to sectoral categories. | # D | # D | # A | # A |  |
| PI-9 | Oversight of aggregate fiscal risk from other public sector entities | D | D+ | D+ | A |  |
|  | # (i) Extent of central government monitoring of AGAs and PEs. | # D | # D | # D | # A |  |
|  | # (ii) Extent of central government monitoring of SN government's fiscal position | # D | # A | # A | # A |  |
| PI-10 | Public access to key fiscal information | C | B | B | A |  |
|  | # (i) Number of the listed elements of public access to information that is fulfilled | # C | # B | # B | # A |  |
|  | C. BUDGET CYCLE |  |  |  |  |  |
|  | C(i) Policy based Budgeting |  |  |  |  |  |
| PI-11 | Orderliness and participation in the annual budget process | C | B | C+ | B+ |  |
|  | # (i) Existence of and adherence to a fixed budget calendar; | # C | # B | # B | # A |  |
|  | # (ii) Clarity/ comprehensiveness of and political involvement in the guidance on the preparation of budget submissions (budget circular or equivalent); | # C | # B | # C | # A |  |
|  | # (iii) Timely budget approval by the legislature or similarly mandated body {or Sector Minister} (within the last three years); | # C | # C | # C | # B |  |
| PI-12 | Multi-year perspective in fiscal planning, expenditure policy and budgeting | D+ | C+ | C+ | A |  |
|  | # (i) Preparation of multi -year fiscal forecasts and functional allocations | # D | # C | # C | # A |  |
|  | # (ii) Scope and frequency of debt sustainability analysis | # C | # A | # A | # A |  |
|  | # (iii) Existence of sector strategies with multi-year costing of recurrent and investment expenditure; | # D | # B | # C | # A |  |
|  | # (iv) Linkages between investment budgets and forward expenditure estimates. | # D | # D | # D | # A |  |
|  | C(ii) Predictability and Control in Budget Execution |  |  |  |  |  |
| PI-13 | Transparency of taxpayer obligations and liabilities | D+ | C | C+ | B+ |  |
|  | # (i) Clarity and comprehensiveness of tax liabilities | # C | # C | # C | # A |  |
|  | # (ii) Taxpayer access to information on tax liabilities and administrative procedures. | # C | # C | # B | # A |  |
|  | # (iii) Existence and functioning of a tax appeals mechanism. | # D | # C | # C | # B |  |
| PI-14 | Effectiveness of measures for taxpayer registration and tax assessment | D+ | C | C+ | A |  |
|  | # (i) Controls in the taxpayer registration system. | # C | # C | # B | # A |  |
|  | # (ii) Effectiveness of penalties for non-compliance with registration and declaration obligations | # D | # C | # C | # A |  |
|  | # (iii) Planning and monitoring of tax audit and fraud investigation programs. | # D | # C | # C | # A |  |
| PI-15 | Effectiveness in collection of tax payments | D+ | D+ | D+ | A |  |
|  | # (i) Collection ratio for gross tax arrears, being the percentage of tax arrears at the beginning of a fiscal year, which was collected during that fiscal year (average of the last two fiscal years). | # D | # D | # D | # A |  |
|  | # (ii) Effectiveness of transfer of tax collections to the Treasury by the revenue administration. | # B | # B | # A | # A |  |
|  | # (iii) Frequency of complete accounts reconciliation between tax assessments, collections, arrears records and receipts by the Treasury. | # D | # D | # D | # A |  |
| PI-16 | Predictability in the availability of funds for commitment of expenditures | D+ | B+ | B+ | A |  |
|  | # (i) Extent to which cash flows are forecast and monitored. | # D | # A | # A | # A |  |
|  | # (ii) Reliability and horizon of periodic in-year information to MDAs on ceilings for expenditure commitment | # B | # B | # B | # A |  |
|  | # (iii) Frequency and transparency of adjustments to budget allocations, which are decided above the level of management of MDAs. | # B | # B | # B | # A |  |
| PI-17 | Recording and management of cash balances, debt and guarantees | C+ | B+ | B+ | A |  |
|  | # (i) Quality of debt data recording and reporting | # D | # B | # A | # A |  |
|  | # (ii) Extent of consolidation of the government’s cash balances | # C | # B | # B | # A |  |
|  | # (iii) Systems for contracting loans and issuance of guarantees. | # A | # A | # B | # A |  |
| PI-18 | Effectiveness of payroll controls | C | C+ | B | A |  |
|  | # (i) Degree of integration and reconciliation between personnel records and payroll data. | # C | # B | # B | # A |  |
|  | # (ii) Timeliness of changes to personnel records and the payroll | # C | # B | # B | # A |  |
|  | # (iii) Internal controls of changes to personnel records and the payroll. | # C | # B | # B | # A |  |
|  | # (iv) Existence of payroll audits to identify control weaknesses and/or ghost workers. | # C | # C | # B | # A |  |
| PI-19 | Competition, value for money and controls in procurement | D+ | C+ | B+ | A |  |
| # i and ii | # (i) Transparency, comprehensiveness and competition in the legal and regulatory framework | # D | # C | # A | # A |  |
| # i and ii | # (ii) Use of competitive procurement methods | # B | # B | # B | # A |  |
|  | # (iii) Public access to complete, reliable and timely procurement information | # D | # C | # A | # A |  |
| # iii | # iv) Existence of an independent administrative procurement complaints system. | # D | # B | # B | # A |  |
| PI-20 | Effectiveness of internal controls for non-salary expenditure | C | C+ | C+ | B+ |  |
|  | # (i) Effectiveness of expenditure commitment controls. | # C | # B | # A | # A |  |
|  | # (ii) Comprehensiveness, relevance and understanding of other internal control rules/ procedures | # C | # C | # B | # A |  |
|  | # (iii) Degree of compliance with rules for processing and recording transactions | # C | # C | # C | # B |  |
| PI-21 | Effectiveness of internal audit | C | C | C | A |  |
|  | # (i) Coverage and quality of the internal audit function. | # C | # C | # C | # A |  |
|  | # (ii) Frequency and distribution of reports | # C | # C | # C | # A |  |
|  | # (iii) Extent of management response to internal audit findings | # C | # C | # C | # A |  |
|  | C(iii) Accounting, Recording and Reporting |  |  |  |  |  |
| PI-22 | Timeliness and regularity of accounts reconciliation | C+ | B | B | A |  |
|  | # (i) Regularity of bank reconciliations | # C | # B | # B | # A |  |
|  | # (ii) Regularity of reconciliation and clearance of suspense accounts and advances. | # B | # B | # B | # A |  |
| PI-23 | Availability of information on resources received by service delivery units | D | D | C | A |  |
|  | # (i) Collection and processing of information to demonstrate the resources that were actually received (in cash and kind) by the most common front-line service delivery units (focus on primary schools and primary health clinics) in relation to the overall resources made available to the sector(s), irrespective of which level of government is responsible for the operation and funding of those units. | # D | # D | # C | # A |  |
| PI-24 | Quality and timeliness of in-year budget reports | C | C+ | C+ | A |  |
|  | # (i) Scope of {sector} reports in terms of coverage and compatibility with budget estimates | # C | # C | # C | # A |  |
|  | # (ii) Timeliness of the issue of reports | # C | # A | # A | # A |  |
|  | # (iii) Quality of information | # C | # A | # A | # A |  |
| PI-25 | Quality and timeliness of annual financial statements | D+ | B+ | C+ | A |  |
|  | # (i) Completeness of the financial statements | # D | # B | # A | # A |  |
|  | # (ii) Timeliness of submission of the financial statements | # C | # B | # A | # A |  |
|  | # (iii) Accounting standards used | # D | # A | # C | # A |  |
|  | C(iv) External Scrutiny and Audit |  |  |  |  |  |
| PI-26 | Scope, nature and follow-up of external audit | D+ | C | C+ | A |  |
|  | # (i) Scope/nature of audit performed (incl. adherence to auditing standards). | # D | # C | # C | # A |  |
|  | # (ii) Timeliness of submission of audit reports to legislature. | # C | # C | # B | # A |  |
|  | # (iii) Evidence of follow up on audit recommendations. | # C | # C | # C | # A |  |
| PI-27 | Legislative scrutiny of the annual budget law | D | B+ | B+ | B+ |  |
|  | # (i) Scope of the legislature’s scrutiny. | # D | # A | # B | # B |  |
|  | # (ii) Extent to which the legislature’s procedures are well-established and respected. | # D | # B | # A | # A |  |
|  | # (iii) Adequacy of time for the legislature to provide a response to budget proposals . | # D | # B | # B | # A |  |
|  | # (iv) Rules for in-year amendments to the budget without ex-ante approval by the legislature. | # D | # A | # B | # A |  |
| PI-28 | Legislative scrutiny of external audit reports | D | C+ | C+ | B |  |
|  | # (i) Timeliness of examination of audit reports by the legislature (for reports received within the last three years). | # D | # B | # C | # B |  |
|  | # (ii) Extent of hearings on key findings undertaken by the legislature. | # D | # C | # C | # B |  |
|  | # (iii) Issuance of recommended actions by the legislature and implementation by the executive. | # D | # B | # B | # B |  |
|  | D. DONOR PRACTICES |  |  |  |  |  |
| D-1 | Predictability of Direct Budget Support | D | B+ | B+ | A |  |
|  | # (i) Annual deviation of actual budget support from the forecast provided by the donor agencies at least six weeks prior to the government submitting its budget proposals to the legislature (or equivalent approving body). | # D | # B | # B | # A |  |
|  | # (ii) In-year timeliness of donor disbursements (compliance with aggregate quarterly estimates) | # D | # A | # A | # A |  |
| D-2 | Financial information provided by donors for budgeting and reporting on project and program aid | D | D | D+ | A |  |
|  | # (i) Completeness and timeliness of budget estimates by donors for project support. | # D | # D | # A | # A |  |
|  | # (ii) Frequency and coverage of reporting by donors on actual donor flows for project support. | # D | # D | # D | # A |  |
| D-3 | Proportion of aid that is managed by use of national procedures | D | D | D | A |  |
|  | # (i) Overall proportion of aid funds to central government that are managed through national procedures (procurement, payment/ accounting, audit and reporting) | # D | # D | # D | # A |  |

Aspirational Targets for Selected Upgraded PEFA Indicators

| Performance Indicator | 2015 Est | Aspirational & Guiding Targets |  | Meaning |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Medium Term | Longer Term | 2015 Rating | 2015 Comment | Medium Term | Longer Term |
| # Upgraded PEFA: PI-11 Public Investment Management | # D+ | # B | # A |  |  |  |  |
| PI11 (i) Objective economic analysis | D | B | A | The requirements for a ‘C’ rating or higher are not met. | Confirmed for ENV. Risk of no independent review. Independence easy to achieve. Can leapfrog to B, with guidelines also. | At least 50% of major projects in the five major investment MDAs are appraised according to economic analysis as established by national guidelines, and validated by an entity other than the sponsoring MDA. | Major capital investment projects, are appraised according to economic analysis, as established by national guidelines, and validated by an entity other than the sponsoring MDA. |
| PI11 (ii) Costing over the project life cycle | C | B | A | For at least 50 percent (by gross cost) of major projects, at least two MDAs with the most infrastructure projects prepare plans with full life cycle of the investment (including recurrent costs), which are discussed during the budget preparation process and included in MDA project proposals. | Will need data but the big agencies appear ok. Getting regulations done will move to B. Recurrent costs in costing, but may not get included in forward estimates. | Regulations or guidelines, that require comprehensive plans for the full life-cycle costs (including recurrent costs) of the investment to be submitted, exist and are partially implemented and included in MDA project proposals. | Regulations or guidelines, that require comprehensive plans for the full life-cycle costs (including recurrent costs) of the investment to be submitted in MDA project proposals, exist and are implemented. |
| PI11 (iii) Project monitoring and reporting | C | B | A | The two MDAs with the largest share of infrastructure projects have some processes in place to monitor physical and financial progress of project implementation. Project monitoring reports to management are prepared on an ad hoc basis. | B appropriate likely, C to be safe. Then move to B easy. | Major MDAs maintain databases (automated or manual), which may not be complete or entirely accurate, on approved projects, on physical and financial progress of project implementation. Project monitoring reports are made available to management at least annually. | Government maintains complete and accurate databases (), on approved projects, on physical and financial progress of project implementation and estimates of completion rates. Project monitoring reports are made available to management at least quarterly. |
| # Upgraded PEFA: PI-12 Public Asset Management | # D | # C | # B |  |  |  |  |
| PI2 (ii) Quality of central government non-financial asset monitoring | D | C | B | The requirements for a ‘C’ rating or higher are not met. | Not enough fixed asset registers. Makes it difficult to plan. | Fixed asset registers exist. Reports on assets are produced occasionally. | Up to date and substantially complete fixed asset registers exist. Comprehensive management and statistical reports (covering assets and related operations) are produced at least annually and disclosed. |
| PI2 (iii) Transparency in the sale, transfer and disposal of non-financial assets and usage rights | D | C | B | The requirements for a ‘C’ rating or higher are not met. | Disposal legislation unclear | The procedures for the sale, transfer or disposal of non-financial assets and asset usage rights are established in the legislation. | The procedures for the competitive and transparent sale, transfer or disposal of non-financial assets and asset usage rights are established in the legislation and are respected in the majority of cases. |
| # Upgraded PEFA: PI-16 Medium-term perspective in expenditure budgeting | # D+ | # C+ | # B+ |  |  |  |  |
| PI6 (i) Coverage and content of sector strategies | C | B | A | Sector strategies exist for sectors representing at least 25% of primary expenditure with full costing of recurrent and investment expenditure as a basis for annual and medium-term budget proposals. | Same as 2013 | Sector strategies exist for sectors representing at least 50% of primary expenditure with full costing of recurrent and investment expenditure as a basis for annual and medium-term budget proposals. | Sector strategies exist for sectors representing at least 75% of primary expenditure with full costing of recurrent and investment expenditure as a basis for annual and medium-term budget proposals. |
| PI6 (iii) Links between the medium-term framework and annual budgets | D | C | B | The requirements for a 'C' rating or higher are not met. | Same as 2013 | Links between the medium term-framework’s second year estimates and setting of the annual budget for the following fiscal year is clear, for MDAs representing 50% of primary expenditure and any major differences are explained. | Links between the medium-term framework’s second year estimates and setting of the annual budget for the following fiscal year is clear, for MDAs representing 75% of primary expenditure and any major differences are explained |
| # Upgraded PEFA: PI-10 Fiscal risk management | # C | # B+ | # A |  |  |  |  |
| PI0 (i) Extent of central government monitoring of AGAs and PEs | D | A | A | The requirements for a 'C' rating or higher are not met. | Same as 2013 | Central government receives annual audited financial reports from all AGAs and PEs and consolidates all fiscal risk issues into an annual (or more frequent) report, including a discussion of AGAs and PEs quasi-fiscal activities. | Central government receives annual audited financial reports from all AGAs and PEs and consolidates all fiscal risk issues into an annual (or more frequent) report, including a discussion of AGAs and PEs quasi-fiscal activities. |
| PI0 (ii) Extent of central government monitoring of SNGs’ fiscal position | A | A | A | SNG cannot generate fiscal liabilities for central government OR the net fiscal position is monitored at least annually for all levels of SNG and central government consolidates overall fiscal risk into annual (or more frequent) reports. | Same as 2013 | SNG cannot generate fiscal liabilities for central government OR the net fiscal position is monitored at least annually for all levels of SNG and central government consolidates overall fiscal risk into annual (or more frequent) reports. | SNG cannot generate fiscal liabilities for central government OR the net fiscal position is monitored at least annually for all levels of SNG and central government consolidates overall fiscal risk into annual (or more frequent) reports. |
| PI0 (iii) Extent of central government monitoring of explicit contingent liabilities from central government programs and projects | D | C | B | The requirements for a 'C' rating or higher are not met. | No contingent liabilities being tracked. | Explicit contingent liabilities (including PPPs) arising from central government programs/projects are quantified and information is collected by a central agency. | Explicit contingent liabilities (including PPPs) arising from central government programs/projects are quantified and consolidated into an annual report. |
| # Upgraded PEFA: PI-4 Classification of the budget | # D | # B | # A |  |  |  |  |
| PI-4 (i) Extent to which the classification system used for formulation, execution and reporting of the central government’s budget is consistent with international standards. | D | B | A | The requirements for a 'C' rating or higher are not met. | Downgraded from 2013 due to comparability of budgets and accounts and application to current and capital budgets. | Budget formulation, execution and reporting is based on administrative, economic (at least level 3 of the GFS standard – 3 digits) and full functional/sub-functional classification, using GFS/COFOG standards or a classification that can produce consistent documentation according to those standards. | Budget formulation, execution and reporting is based on ALL levels of administrative, economic and functional classification using GFS/COFOG standards, or a classification that can produce consistent documentation according to those standards and is fully consistent with all classifications used for reporting financial information. Program classification may substitute for sub-functional classification, if it is applied with a level of detail at least corresponding to sub-functional classification. |
| Upgraded PEFA: PI-5: Comprehensiveness of information included in budget documentation | D | B | A |  |  |  |  |
| PI-5 (i) Share of the above listed information in the executive’s annual budget proposals most recently issued by the central government (in order to count in the assessment, the full specification of the information benchmark must be met). | D | B | A | The requirements for a 'C' rating or higher are not met. | Downgraded from 2013 due to incomplete basic elements of the budget disclosures. | Budget documentation fulfills all basic elements (1-4) and at least 3 of the additional elements (e.g. Fiscal Risks from PPPs etc). | Budget documentation fulfills all basic elements (1-4) and at least 6 of the additional elements (e.g. Fiscal Risks and contingent liabilities from PPPs etc). |
| # Upgraded PEFA: PI-23 Transparency, competition and complaints mechanisms in procurement | # D | # C | # B |  |  |  |  |
| P23 (i) Monitoring the efficiency and effectiveness of the procurement system | D | C | B | The requirements for “C” rating or higher are not met. | WB contract database not comprehensive. E-Procurement does not cover. | Databases (or records) are maintained for contracts representing at least 50% of expenditure on goods, services and works, including both data elements above. Analysis of this data is made available to management ad hoc. | Databases (or records) are maintained for contracts representing at least 75% of value of procurement of goods, services and works, including both data elements above. Analysis of this data is made available to management at least annually. |
| Upgraded PEFA: PI-8: Performance information for achieving efficiency in service delivery | D+ | B | A |  |  |  |  |
| PI-8 (i) Disclosure of annual performance targets for service delivery | C | B | A | Performance targets are presented for 10-25% of service delivery functions OR coverage is more than 25% but with deficiencies in the format or definition of the targets (outputs) or in the methods of measurement. | Different to PI23. | Performance targets are presented in a format which is clear about what is being measured (outputs) and how it is to be measured (method of calculation and data sources) for 25-50% of service delivery functions. | Performance targets are presented in a format which is clear about what is being measured (outputs) and how it is to be measured (method of calculation and data sources) for more than 50% of service delivery functions. |
| PI-8 (ii) Disclosure of data on performance results achieved by service | C | B | A | Performance targets are presented for 10-25% of service delivery functions OR coverage is more than 25% but with deficiencies in the format or definition of the targets (outputs) or in the methods of measurement. | Different to PI23. | Performance targets are presented in a format which is clear about what is being measured (outputs) and how it is to be measured (method of calculation and data sources) for 25-50% of service delivery functions. | Performance targets are presented in a format which is clear about what is being measured (outputs) and how it is to be measured (method of calculation and data sources) for more than 50% of service delivery functions. |
| PI-8 (iii) Monitoring of resources received by service delivery units | C | B | A | A system exists, for less than 25% of service delivery functions, that monitors if resources have reached service delivery units as planned. | Same score for PI23 | A system exists, for 25-50% of service delivery functions, that monitors if resources have reached service delivery units as planned. | A system exists, in more than 50% of service delivery functions, that monitors if resources have reached service delivery units as planned |
| PI-8 (iv) Content and coverage of independent performance evaluations | D | C | A | The requirements for a 'C' rating or higher are not met. | Different to PI23. Independence criteria not met. | Independent performance evaluations for less than 25% of service delivery function have been undertaken in the last three financial years, and include recommendations for enhancing delivery. | Independent performance evaluations for more than 50% of service delivery functions have been undertaken in the last three financial years, and include recommendations for enhancing delivery. |
| Upgraded PEFA: PI-13: Management and reporting of debt and expenditure arrears | C | B | A |  |  |  |  |
| PI-13 (iv) Stock and monitoring of expenditure arrears | C | B | A | Data on the stock of arrears has been generated by at least one comprehensive ad hoc exercise within the last two years. | NR on PI4=D. Survey is now more than 2 years old. | Data on the stock of arrears is generated annually, but may not be complete for a few identified expenditure categories or specified budget institutions. This data demonstrates that the stock of arrears is no more than 10% of total expenditure. | Complete data on the stock of arrears is generated at least at the end of each fiscal year and includes an age profile - and demonstrates that the stock of arrears is no more than 2% of total expenditure. |
| Upgraded PEFA: PI-25: Effectiveness of internal audit | D+ | B | A |  |  |  |  |
| PI-25 (i) Coverage of the internal audit function (percentages quoted refer to). | C | B | A | Internal audit is operational for central government entities representing at least 50% of total budgeted expenditures and for entities collecting at least 50% of government revenue. | Same as 2013. Still appropriate. | Internal audit is operational for central government entities representing at least 75% of total budgeted expenditures and for entities collecting at least 75% of government revenue. | Internal audit is operational for all central government entities. |
| PI-25 (ii) Implementation of audits and distribution of reports (percentages quoted refer to the average rate of completion of audit plans for all audited entities). | C | B | A | At least 50% of audit plan engagements are completed, as evidenced by distribution of the reports to the appropriate parties. | Same as 2013. Still appropriate. | At least 75% of audit plan engagements are completed, as evidenced by distribution of the reports to the appropriate parties. | At least 90% of audit plan engagements are completed, as evidenced by distribution of the reports to the appropriate parties. |
| PI-25 (iii) Extent of management response to internal audit findings. | C | B | A | There is clear evidence of effective and timely follow up of internal audit findings by management of 50% of the entities audited in the last financial year. | Same as 2013. Still appropriate. | There is clear evidence of effective and timely follow up of internal audit findings by management of 75% of the entities audited in the last financial year. | There is clear evidence of effective and timely follow up of internal audit findings by management of 90% of the entities audited in the last financial year. |
| PI-25 (iv) Nature of audit performed and adherence to professional standards. | D | C | A | The requirements for a ‘C’ rating or higher are not met. | Not sufficient coverage of standards across government. | Internal audit activities consist primarily of ex-post reviews focused on financial compliance. | A quality assurance process is in place within the internal audit function. There is evidence that assurance activities meet professional standards, including following a risk-based audit plan. |

Aspirational OBI Targets

| No. | Question | 2008 | 2010 | 2012 | Aspirational |
| --- | --- | --- | --- | --- | --- |
| 1 | Does the Executive’s Budget Proposal or any supporting budget documentation present expenditures for the budget year that are classified by administrative unit (that is, by ministry, department, or agency)? | 0 | 0 | 100 | 100 |
| 2 | Does the Executive’s Budget Proposal or any supporting budget documentation present expenditures for the budget year by functional classification? | 0 | 0 | 33 | 100 |
| 3 | Does the Executive’s Budget Proposal or any supporting budget documentation present expenditures for the budget year that are presented by economic classification? | 0 | 0 | 100 | 100 |
| 4 | Does the Executive’s Budget Proposal or any supporting budget documentation present expenditures for individual programs for the budget year? | 0 | 0 | 100 | 100 |
| 5 | In the Executive’s Budget Proposal or any supporting budget documentation are estimates of the aggregate level of expenditure presented for a multi-year period (at least two years beyond the budget year)? | 0 | 0 | 100 | 100 |
| 6 | In the Executive’s Budget Proposal or any supporting budget documentation is more detail in addition to the aggregate level presented for expenditure estimates that cover a multi-year period (for at least two years beyond the budget year)? | 0 | 0 | 33 | 100 |
| 7 | Does the Executive’s Budget Proposal or any supporting budget documentation identify the different sources of tax revenue (such as income tax or VAT) for the budget year? | 0 | 0 | 100 | 100 |
| 8 | Does the Executive’s Budget Proposal or any supporting budget documentation identify the different sources of non-tax revenue (such as grants, property income, and sales of government-produced goods and services) for the budget year? | 0 | 0 | 0 | 100 |
| 9 | In the Executive’s Budget Proposal or any supporting budget documentation are estimates of the aggregate level of revenue presented for a multi-year period (at least two years beyond the budget year)? | 0 | 0 | 100 | 100 |
| 10 | In the Executive’s Budget Proposal or any supporting budget documentation is more detail in addition to the aggregate level presented for revenue estimates that cover a multi-year period (for at least two years beyond the budget year)? | 0 | 0 | 100 | 100 |
| 11 | Does the Executive’s Budget Proposal or any supporting budget documentation present data on the total government debt outstanding for the budget year? | 0 | 0 | 33 | 100 |
| 12 | Does the Executive’s Budget Proposal or any supporting budget documentation present interest payments on the debt for the budget year? | 0 | 0 | 100 | 100 |
| 13 | Does the Executive’s Budget Proposal or any supporting budget documentation present information related to the composition of government debt (such as interest rates on the debt, maturity profile of the debt, currency denomination of the debt, or whether it is domestic or external debt) for the budget year? | 0 | 0 | 67 | 100 |
| 14 | Does the Executive’s Budget Proposal or any supporting budget documentation present the macroeconomic forecast upon which the budget projections are based? | 0 | 0 | 67 | 100 |
| 15 | Does the Executive’s Budget Proposal or any supporting budget documentation show the impact of different macroeconomic assumptions (i.e., sensitivity analysis) on the budget (including impacts on expenditures, revenues, and debt)? | 0 | 0 | 67 | 100 |
| 16 | Does the Executive’s Budget Proposal or any supporting budget documentation present information for at least the budget year that shows how policy proposals, as distinct from existing policies, affect expenditures? | 0 | 0 | 33 | 100 |
| 17 | Does the Executive’s Budget Proposal or any supporting budget documentation present information for at least the budget year that shows how policy proposals, as distinct from existing policies, affect revenues? | 0 | 0 | 33 | 100 |
| 18 | Does the Executive’s Budget Proposal or any supporting budget documentation present expenditures for the year preceding the budget year (BY-1) that are classified by administrative unit (that is, by ministry, department, or agency)? | 0 | 0 | 100 | 100 |
| 19 | Does the Executive’s Budget Proposal or any supporting budget documentation present expenditures for the year preceding the budget year (BY-1) that are classified by functional classification? | 0 | 0 | 33 | 100 |
| 20 | Does the Executive’s Budget Proposal or any supporting budget documentation present expenditures for the year preceding the budget year (BY-1) that are classified by economic classification? | 0 | 0 | 33 | 100 |
| 21 | Does the Executive’s Budget Proposal or any supporting budget documentation present expenditures for individual programs for the year preceding the budget year (BY-1)? | 0 | 0 | 100 | 100 |
| 22 | In the Executive’s Budget Proposal or any supporting budget documentation, how many months of data on actual expenditures are reflected in the expenditure estimates of the year prior to the budget year (BY-1)? | 0 | 0 | 0 | 100 |
| 23 | In the Executive’s Budget Proposal or any supporting budget documentation are estimates of the aggregate level of expenditure presented for more than one year prior to the budget year (that is, BY-2 and prior years)? | 0 | 0 | 100 | 100 |
| 24 | Does the Executive’s Budget Proposal or any supporting budget documentation present more detail in addition to the aggregate level for expenditure estimates that cover more than one year prior to the budget year (that is, BY-2 and prior years)? | 0 | 0 | 67 | 100 |
| 25 | In the Executive’s Budget Proposal or any supporting budget documentation, what is the most recent year presented for which all expenditures reflect actual outcomes? | 0 | 0 | 100 | 100 |
| 26 | Are the expenditure estimates for the years prior to the budget year adjusted as needed to be comparable with the budget-year estimates in terms of classification and presentation? | 0 | 0 | 100 | 100 |
| 27 | Does the Executive’s Budget Proposal or any supporting budget documentation identify the different sources of tax revenue (such as income tax or VAT) for the year preceding the budget year (BY-1)? | 0 | 0 | 67 | 100 |
| 28 | Does the Executive’s Budget Proposal or any supporting budget documentation identify the different sources of non-tax revenue (such as grants, property income, and sales of goods and services) for the year preceding the budget year (BY-1)? | 0 | 0 | 67 | 100 |
| 29 | In the Executive’s Budget Proposal or any supporting budget documentation, how many months of data on actual revenues are reflected in the revenue estimates of the year prior to the budget year (BY-1)? | 0 | 0 | 100 | 100 |
| 30 | In the Executive’s Budget Proposal or any supporting budget documentation are estimates of the aggregate level of revenues presented for more than one year prior to the budget year (that is, BY-2 and prior years)? | 0 | 0 | 100 | 100 |
| 31 | In the Executive’s Budget Proposal or any supporting budget documentation is more detail in addition to the aggregate level presented for revenue estimates for more than one year prior to the budget year (that is, BY-2 and prior years)? | 0 | 0 | 67 | 100 |
| 32 | In the Executive’s Budget Proposal or any supporting budget documentation, what is the most recent year presented for which all revenues reflect actual outcomes? | 0 | 0 | 100 | 100 |
| 33 | Does the Executive’s Budget Proposal or any supporting budget documentation present information related to the government debt for the year preceding the budget year? | 0 | 0 | 67 | 100 |
| 34 | In the Executive’s Budget Proposal or any supporting budget documentation, what is the most recent year presented for which the debt figures reflect actual outcomes? | 0 | 0 | 100 | 100 |
| 35 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on extra-budgetary funds for at least the budget year? | 0 | 0 | -1 | 100 |
| 36 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on intergovernmental transfers for at least the budget year? | 0 | 0 | -1 | 100 |
| 37 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on transfers to public corporations for at least the budget year? | 0 | 0 | 100 | 100 |
| 38 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on quasi-fiscal activities for at least the budget year? | 0 | 0 | -1 | 100 |
| 39 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on financial assets held by the government? | 0 | 0 | 0 | 100 |
| 40 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on nonfinancial assets held by the government? | 0 | 0 | 33 | 100 |
| 41 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on expenditure arrears for at least the budget year? | 0 | 0 | 0 | 100 |
| 42 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on contingent liabilities (such as government loan guarantees)? | 0 | 0 | 33 | 100 |
| 43 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on future liabilities, such as civil service pensions? | 0 | 0 | 0 | 100 |
| 44 | Does the Executive’s Budget Proposal or any supporting budget documentation provide details on the sources of donor assistance, both financial and in-kind? | 0 | 0 | 33 | 100 |
| 45 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on tax expenditures for at least the budget year? | 0 | 0 | 0 | 100 |
| 46 | Does the Executive’s Budget Proposal or any supporting budget documentation identify all earmarked revenues? | 0 | 0 | 100 | 100 |
| 47 | What percentage of expenditure in the budget year is dedicated to spending on secret items relating to, for instance, national security and military intelligence? | 0 | 0 | 67 | 100 |
| 48 | Does the Executive’s Budget Proposal or any supporting budget documentation explain how the proposed budget is linked to government’s stated policy goals, by administrative unit or functional category, for the budget year? | 0 | 0 | 67 | 100 |
| 49 | Does the Executive’s Budget Proposal or any supporting budget documentation explain how the proposed budget is linked to government’s stated policy goals for a multi-year period (for at least two years beyond the budget year)? | 0 | 0 | 33 | 100 |
| 50 | Does the Executive’s Budget Proposal or any supporting budget documentation present nonfinancial data, such as the number of beneficiaries, for expenditure programs? | 0 | 0 | 100 | 100 |
| 51 | Are the nonfinancial data presented useful for assessing how an expenditure program is performing? | 0 | 0 | 100 | 100 |
| 52 | Does the Executive’s Budget Proposal or any supporting budget documentation contain performance indicators for expenditure programs? | 0 | 0 | 100 | 100 |
| 53 | Are the performance indicators sufficiently well designed, such that one can assess whether there has been progress toward meeting policy goals? | 0 | 0 | 67 | 100 |
| 54 | Are performance indicators used in conjunction with performance targets presented in the Executive’s Budget Proposal or any supporting budget documentation? | 0 | 0 | 67 | 100 |
| 55 | Does the Executive’s Budget Proposal or any supporting budget documentation present information on policies (both proposals and existing commitments) that are intended to benefit directly the country’s most impoverished populations in at least the budget year? | 0 | 0 | 33 | 100 |
| 56 | How far in advance of the release of the budget is the day of its release known? | 0 | 100 | 100 | 100 |
| 57 | Does the executive release to the public its timetable for formulating the Executive’s Budget Proposal (that is, a document setting deadlines for submissions from other government entities, such as line ministries or subnational government, to the Ministry of Finance or whatever central government agency is in charge of coordinating the budget’s formulation)? | 100 | 100 | 100 | 100 |
| 58 | Does the executive adhere to its timetable for the preparation and release of the budget? | 100 | 67 | 67 | 67 |
| 59 | Does the executive hold consultations with members of the legislature as part of its process of determining budget priorities? | 33 | 0 | 0 | 67 |
| 60 | When does the executive release a Pre-Budget Statement to the public? | 0 | 0 | 100 | 100 |
| 61 | Does the Pre-Budget Statement describe the government’s macroeconomic and fiscal framework? | 0 | 0 | 100 | 100 |
| 62 | Does the Pre-Budget Statement describe the government’s policies and priorities that will guide the development of detailed estimates for the upcoming budget? | 0 | 0 | 100 | 100 |
| 63 | How often does the executive release to the public In-Year Reports on actual expenditure (organized by administrative unit, economic classification, and/or function)? | 100 | 100 | 100 | 100 |
| 64 | What share of expenditure is covered by In-Year Reports on actual expenditure (organized by administrative unit, economic classification, and/or function)? | 100 | 100 | 100 | 100 |
| 65 | What is the most detail provided in the In-Year Reports on actual expenditures organized by administrative unit? | 67 | 33 | 100 | 100 |
| 66 | Do the In-Year Reports released to the public compare actual year-to-date expenditures with either the original estimate for that period (based on the enacted budget) or the same period in the previous year? | 0 | 100 | 100 | 100 |
| 67 | How often does the executive release to the public In-Year Reports on actual revenue collections by source of revenue? | 100 | 100 | 100 | 100 |
| 68 | What share of revenue is covered by the In-Year Reports on actual revenue collections? | 100 | 100 | 100 | 100 |
| 69 | Do the In-Year Reports released to the public compare actual year-to-date revenue collections with either the original estimate for that period (based on the enacted budget) or the same period in the previous year? | 0 | 100 | 100 | 100 |
| 70 | Does the executive release to the public In-Year Reports on actual borrowing? | 0 | 100 | 100 | 100 |
| 71 | Do In-Year Reports released to the public on actual borrowing present information related to the composition of government debt (such as interest rates on the debt, maturity profile of the debt, and currency denomination of the debt) for the budget year? | 0 | 0 | 0 | 67 |
| 72 | For In-Year Reports on actual expenditure released to the public by the executive, how much time typically elapses between the end of the reporting period and when the report is released (e.g., are quarterly reports released less than four weeks after the end of the quarter)? | 100 | 100 | 33 | 100 |
| 73 | Does the executive release to the public a Mid-Year Review of the budget that discusses the changes in economic outlook since the budget was enacted? | 0 | 100 | 0 | 67 |
| 74 | Does the executive release to the public a Mid-Year Review of the budget that includes updated expenditure estimates for the budget year underway? | 0 | 100 | 0 | 67 |
| 75 | What is the most detail provided in the Mid-Year Review for expenditures? | 0 | 67 | 0 | 67 |
| 76 | Does the executive release to the public a Mid-Year Review of the budget that includes updated revenue estimates for the budget year underway? | 0 | 100 | 0 | 67 |
| 77 | How long after the end of the budget year does the executive release to the public a Year-End Report that discusses the budget’s actual outcome for the year? | 100 | 100 | 100 | 100 |
| 78 | In the Year-End Report have the data on the actual outcomes been audited? | 0 | 0 | 0 | 100 |
| 79 | Does the Year-End Report explain the differences between the enacted levels (including in-year changes approved by the legislature) and the actual outcome for expenditures? | 0 | 0 | 67 | 100 |
| 80 | What level of detail is the focus of the explanation of the differences between the enacted levels and the actual outcome for expenditures presented in the Year-End Report? | 0 | 0 | 67 | 100 |
| 81 | Does the Year-End Report explain the differences between the enacted levels (including in-year changes approved by the legislature) and the actual outcome for revenues? | 0 | 100 | 67 | 100 |
| 82 | Does the Year-End Report explain the differences between the original macroeconomic forecast for the fiscal year and the actual outcome for that year? | 0 | 67 | 33 | 100 |
| 83 | Does the Year-End Report explain the differences between the original estimates of nonfinancial data and the actual outcome? | 0 | 0 | 0 | 100 |
| 84 | Does the Year-End Report explain the differences between the original performance indicators and the actual outcome? | 0 | 0 | 0 | 100 |
| 85 | Does the Year-End Report explain the differences between the enacted level of funds intended to benefit directly the country’s most impoverished populations and the actual outcome? | 0 | 0 | 0 | 100 |
| 86 | Does the Year-End Report present the actual outcome for extra-budgetary funds? | 0 | 0 | -1 | 100 |
| 87 | How long after the end of the fiscal year are the final annual expenditures of national departments audited and the results of the audits (except for secret programs) released to the public? | 0 | 67 | 0 | 100 |
| 88 | Two years after the end of a fiscal year, what percentage of annual expenditures has been audited and included in (except for secret programs) the Audit Report(s) released to the public? | 0 | 67 | 0 | 100 |
| 89 | Does the annual Audit Report(s) that is released to the public include an executive summary? | 0 | 100 | 0 | 100 |
| 90 | Must a branch of government other than the executive (such as the legislature or the judiciary) give final consent before the head of the supreme audit institution (SAI) can be removed from office? | 0 | 0 | 0 | 100 |
| 91 | Does the supreme audit institution (SAI) release to the public audits of extra-budgetary funds? | 0 | 0 | 0 | 67 |
| 92 | Beyond the established year-end attestation audits, does the supreme audit institution (SAI) have the discretion in law to undertake those audits it may wish to? | 0 | 0 | 100 | 100 |
| 93 | Who determines the budget of the supreme audit institution (SAI)? | 67 | 100 | 100 | 100 |
| 94 | Does the supreme audit institution (SAI) employ designated staff to undertake audits of the central government agencies pertaining to the security sector (military, police, intelligence services)? | 0 | 100 | 100 | 100 |
| 95 | Does the executive make available to the public a report on what steps it has taken to address audit recommendations or findings that indicate a need for remedial action? | 0 | 0 | 0 | 67 |
| 96 | Are Audit Reports of the annual accounts of the security sector (military, police, intelligence services) and other secret programs provided to the legislature (or relevant committee)? | 0 | 0 | 0 | 67 |
| 97 | Does the legislature have internal capacity to conduct budget analyses or access to independent research capacity for such analyses? | -1 | -1 | 67 | 67 |
| 98 | Does the legislature formally debate the overall budget policy prior to the tabling of the Executive’s Budget Proposal? | -1 | -1 | 33 | 67 |
| 99 | How far in advance of the start of the budget year does the legislature receive the Executive’s Budget Proposal? | 67 | 67 | 33 | 67 |
| 100 | Does the legislature have the authority in law to amend the Executive’s Budget Proposal? | 0 | 33 | 67 | 67 |
| 101 | What is the highest level of detail provided for appropriations (expenditure budget) in the Enacted Budget approved by the legislature? | 67 | 100 | 100 | 100 |
| 102 | Is the executive required by law or regulation to seek input from the legislature when it shifts funds between administrative units that receive explicit funding through the annual budget? | 0 | 100 | 33 | 100 |
| 103 | Is the executive required seek input from the legislature when it shifts funds between line items (except when the amounts are below a certain minimal level specified in law or regulation)? | -1 | -1 | 0 | 67 |
| 104 | What legal or regulatory restrictions are in place on the executive’s discretion to spend excess revenue that may become available during the budget execution period? | -1 | -1 | 100 | 100 |
| 105 | When does the legislature typically approve supplemental budgets? | -1 | 100 | 100 | 100 |
| 106 | When does the legislature approve the expenditure of contingency funds or other funds for which no specific purpose was identified in the Enacted Budget? | 100 | 100 | 0 | 100 |
| 107 | Does a committee of the legislature view and scrutinize the audit reports? | 0 | 0 | 100 | 100 |
| 108 | Does either the supreme audit institution or legislature release to the public a report that tracks actions taken by the executive to address audit recommendations? | 0 | 0 | 0 | 67 |
| 109 | What is the most detail provided by the Citizens Budget? | 0 | 0 | 100 | 100 |
| 110 | How is the Citizens Budget disseminated to the public? | -1 | -1 | 100 | 100 |
| 111 | Are the public’s priorities on budget information taken into consideration by the executive while drafting the Citizens Budget? | -1 | -1 | 0 | 100 |
| 112 | Are Citizens Budget throughout the budget process? | -1 | -1 | 33 | 100 |
| 113 | Does the executive make available to the public accessible, nontechnical definitions of terms used in the budget and other budget-related documents (for instance, in a glossary)? | 33 | 0 | 0 | 100 |
| 114 | Is the executive formally required to engage with the public during the budget process? | -1 | -1 | 33 | 67 |
| 115 | Does the executive clearly, and in a timely manner, articulate its purpose for engaging the public during the budget formulation and execution processes? | -1 | -1 | 33 | 100 |
| 116 | Has the executive established practical and accessible mechanisms to identify the public’s perspective on budget priorities? | -1 | -1 | 33 | 67 |
| 117 | Has the executive established practical and accessible mechanisms to identify the public’s perspective on budget execution? | -1 | -1 | 0 | 67 |
| 118 | Does the executive provide formal, detailed feedback to the public on how its inputs have been used to develop budget plans and improve budget execution? | -1 | -1 | 0 | 67 |
| 119 | Does a legislative committee (or committees) hold public hearings on the macroeconomic and fiscal framework presented in the budget in which testimony from the executive branch and the public is heard? | 0 | 33 | 0 | 67 |
| 120 | Do legislative committees hold public hearings on the individual budgets of central government administrative units (i.e., ministries, departments, and agencies) in which testimony from the executive branch is heard? | 0 | 33 | 33 | 67 |
| 121 | Does a legislative committee (or committees) hold public hearings on the individual budgets of central government administrative units (i.e., ministries, departments, and agencies) in which testimony from the public is heard? | 0 | 0 | 0 | 67 |
| 122 | Do the legislative committees that hold public hearings release reports to the public on these hearings? | 0 | 0 | 0 | 67 |
| 123 | Does the supreme audit institution (SAI) maintain formal mechanisms through which the public can participate in the audit process? | 0 | 0 | 0 | 67 |
| 124 | Does the SAI maintain any communication with the public regarding its audit reports beyond simply making these reports publicly available? | -1 | -1 | 0 | 67 |
| 125 | Does the supreme audit institution (SAI) provide formal, detailed feedback to the public on how their inputs have been used to determine its audit program or in audit reports? |  | -1 | 0 | 67 |

Statistical Capacity Indicators

| SCI | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | ASP TARGET |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Overall score | 24 | 31 | 32 | 34 | 46 | 47 | 52 | 51 | 50 | 53 | 54 | 73 |
| Compliance with Methodology | 0 | 20 | 20 | 20 | 40 | 30 | 40 | 40 | 40 | 50 | 50 | 70 |
| Adequacy of source data | 20 | 20 | 20 | 20 | 30 | 40 | 40 | 40 | 40 | 40 | 40 | 60 |
| Periodicity and timeliness | 53 | 53 | 57 | 63 | 67 | 70 | 77 | 73 | 70 | 70 | 73 | 90 |

## Attachment C: “Basics first”

The foundation theory for change and/or design principles presented here help to establish a performance management culture within Government. The theory has five mutually reinforcing idealised approaches to delivering aid effectively and programming PFM reforms. These five components are:

Conform to aid effectiveness principles of ownership, alignment, harmonisation, managing for results, mutual accountability and the G7+ TRUST and FOCUS priorities;

Follow the Basics First and Platform Approach to help prioritize and sequencing PFM reform activities over time;

Target the weakest links in the continuous improvement cycle to ensure the system is self-improving;

Utilise analytical techniques to continually assess technical and political feasibility of reforms and reform options; and

Introduce a Team-based Performance Management culture starting with integrating team-based performance management into reform program design and monitoring and evaluation systems.

## Attachment D: Budget Support Policy Framework

The purpose of this section is to provide an outline of a proposal by the Government to establish a framework to support implementation of the Public Financial Management Roadmap II. This PFMRII Program Budget Support Framework (the Framework) forms a part of the Government’s broader foreign assistance and aid management policy. This section provides a short summary of key areas for the Government and development partners to discuss with the view to securing in-principle agreements. Once reached, these future agreements could form the basis of more formal financing instruments (grant agreements) made with individual development partners who wish to participate in the budget support arrangements for the PFMRII.

The Framework will be subject to independent assessments that general preconditions or eligibility criteria for budget support set by different development partners are in place. While the precise preconditions will need to be negotiated, they can be broadly summarized in the following five areas:

- Macroeconomic stability: There must be a credible plan for macroeconomic and fiscal sustainability which is reflected in a Medium Term Macro-Fiscal Framework;

- A strategy for reform: There needs to be a credible plan for Public Financial Management reforms over at least 5 years that supports the broader policy objectives of sustainable and inclusive growth, democratic governance and poverty reduction;

- Budget transparency: The Government must publish the budget as agreed by the national parliament and include the medium term fiscal outlook and estimates for Government revenue and expenditure for at least the current and two forward years.  The Government must also commit to produce timely and complete reports on budget outcomes for previous years expenditure that can be compared to the original budget as published;

- Political Commitment: The reform planning and implementation processes for PFMRII must have consistent and public support from the President and the Cabinet; and

- Risk Management: The level of fiduciary risk from development partners using Afghan national systems must not be significantly higher than using alternative arrangements that by-pass country systems. The level of development risk of development partners using country systems must be unambiguously lower than alternative arrangements.

The partnership principles developed by the g7+ and set out in the New Deal provide a good basis for partnerships between the Government and donors:

FOCUS on supporting inclusive country-led and country-owned transitions out of fragility (especially support for one vision, one plan, political dialogue and leadership); and

TRUST (Transparency, Risk-sharing, Use and strengthening country systems, Strengthening capacities and Timely and predictable aid) by providing aid and managing resources more effectively and aligning these resources for results.

Summary of Design Elements for the Budget Support Framework:

Ideally the Government will negotiate a program with a Medium-term, earmarked (program), direct budget support facility following a programmatic structure and utilizing general and specific but floating conditions with performance based but untargeted financial assistance following a system of fixed and variable tranches.

In plain language the Government should seek support from its partners over 5 years, for its rolling plans for fiscal performance improvement under the PFMRII, using both general and program specific indicators that can be monitored and updated over the period of the program, through performance payments in the form of fixed upfront commitments and variable, performance based payments based on outcomes and outputs achieved.

The Government and development partners will need to reach agreement on the design elements of a budget support arrangement. Table 1 provides a brief explanation of a range of possible design elements.

Explanations of Sector Budget Support Design Elements

| 1. Medium-term timeframe | The PFMRII and the subsequent Fiscal Performance Improvement Plan to implement the PFMRII over the next 5 years from 2016 to 2020 (1395 – 1399). Most of the reforms will take multiple years while some will be ongoing after the life of this program. Design of support therefore needs to be over the medium-term and be flexible to adjust to changed context and progress during the 5 years. |
| --- | --- |
| 2. Program or Sector Budget Support | To support implementation of the PFMRII through the Fiscal Performance Improvement Plan and team-based performance management. In this instance, it is hard to define a sector for what is more typically termed “sector budget support”. Program budget support, in this case the program being PFMRII, should include linkages to all key PFM areas including service delivery, audit and procurement. |
| 3. Direct Budget Support | Delivery of foreign currency denominated foreign assistance channelled to the Government via existing national systems, or if necessary through channels specifically designed for the purpose of this program. |
| 4. Programmatic Structure | A joint monitoring matrix of Mutually Agreeable Results is set annually based on the Government’s strategic plans and Annual Action Planning process (i.e. not a multi-tranche operation, although a predictable multi-year resource envelope should be established). |
| 5. General and specific conditions | General conditions are eligibility conditions for a program to start and continue. Specific conditions related to conditions for disbursement of aid – i.e. what constitutes satisfactory performance. These specific conditions will need to be designed in a way that helps: i) frame policy dialogue between the Government and development partners; ii) manage fiduciary and development risks; and iii) provide clarity on mutual obligations. |
| 6. Floating conditions | Deadlines associated with Mutually Agreeable Results (MARs) targets and tranche disbursements are indicative and not fixed. Provides flexibility in keeping with principles of a partnership approach and risk sharing. The floating nature of the conditionality requires an extensive Joint Monitoring Matrix (JMM), based on the Government’s 5-year action plans, and should include high and medium priority action-based performance targets for results. Satisfactory performance would be graded (F, D to A+) for each MAR and aggregated for each administrative unit (National Directorate and Units) based on three criteria (timeliness, quality, effectiveness in dealing with problems weighted for the level of technical assistance employed). MARs that are not reached may rollover to the following year in full or in amended form. |
| 7. Untargeted financial assistance | Eligibility of expenditures limited to intended purpose as reflected in programs, activities and budget line items identified in the Government’s strategic Plans, Annual Action Planning and budget processes. However, development partners can indicate a preference for earmarking of their money for particular purpose or budget line item. No ineligible expenditures (black lists) outside this (i.e. not targeting “professional services”). This increases flexibility and promotes dialogue around strategic program, annual action plans and performance. |
| 8. Ex-ante and ex-poste financial assistance | Ex-ante financial assistance enables predictability of resources, promotes in-year dialogue around performance and helps management of risk. |
|  | - Ex-ante financing (funds provided in advance of expenditure) is primary. |
|  | - Ex-poste financing (reimbursement) of specific expenditures within the budget or of specific budget lines as agreed during the year allowed based on need, performance and availability of foreign assistance. |
| 9. Fixed and Variable Tranches | Fixed tranches deliver predictability of resourcing. Variable tranches based on performance deliver positive incentives and stronger risk management. Tranches should be set-up within the budget cycle. Review of performance during October to December will determine the level of total (fixed and variable) budget support for the following fiscal year and will be fixed for that year. Poor performance on MARS during the year will have no impact on levels of foreign assistance delivered in that same year, other than in the situation of manifestly poor budget execution performance and the use of budget support funds. In-year variable tranches also possible (see ex-poste financing above). |

Other Key Budget Support Implementation Elements

Other implementation elements are required. In addition to the eligibility criteria and key design elements above, the Government and interested development partners will also need to agree to other key budget support implementation mechanisms such as a Joint Monitoring and Evaluation Mechanism; fixed and variable payment mechanisms and timing; budget and accounting treatments and fund Flows; and procurement.

A) Establishing a Joint Monitoring and Evaluation Mechanism

A Joint Monitoring and Evaluation Mechanism built around the budget cycle and national systems. A Joint Monitoring Matrix (JMM) of Mutually Agreeable Results (MARs) as a foundation for monitoring of progress on reform and institutional strengthening plans and managing risk. Key features might include the following:

JMM and MARS discussion with development partners prior to the beginning of a fiscal year around the time the national budget is prepared (possibly Sep-October).

Development partners can choose up to 12 major or high priority actions from the JMM each year for focus under the performance management system and specify tranche payments (fixed and variable) to provide some predictability to the flow of program support to the PFMRII;

Independent in year monitoring against JMM and MARS with development partners twice a year in May and October in line with the budget cycle.

May and October Reviews – May would be a progress update with indicative performance ratings against actions with an internal report provided to the Government and development partners. The October review would be the formal annual performance assessment where team performance assessments and a formal Annual Performance Report are finalised and published by the Government. This formal assessment forms the basis for flexible or incentive payments as well as informing negotiations for the following year’s MARs and tranche payments. Development partners may want to nominate independent consultants to participate in reviews as they feel appropriate and as agreed with the Government.

Progress based on satisfactory progress against MARs as expressed in the Joint Monitoring Matrix (JMM), which would be a sub-set of actions drawn from the Government’s 5-year action plans. Performance would be graded (D to A+) for each MAR and aggregated for each administrative unit (Directorate and Units) based on three criteria (timeliness, quality, effectiveness in dealing with problems weighted for the level of technical assistance employed). Satisfactory performance should be C or above. The direction of change in performance is also important i.e. even if performance is below satisfactory - is there progress? MARs that fall short of targets might be rolled-over to the following year in full or in amended form. Medium term outcome indicators reviewed annually.

Proposed budgets for the following year discussed with development partners prior to the next fiscal year, ideally around the time the national budget is prepared (around Sep-October).

Formal PEFA assessments would be undertaken every three years with the next assessment in late 2016.

  - Key PEFA aspirational targets might be recalculated on an annual basis or as agreed through the JMM process.

  - Other international and independently assessed benchmarks considered and agreed through the JMM process (e.g. Open Budget Index, Revenue Watch transparency indictors etc.).

A joint mid-term evaluation of the budget support arrangement planned for some time in 2018.

B) Fixed and variable payment mechanism and timing

Fixed payments mean a tranche payment made in advance of the next fiscal year based on agreed MARs and previous performance. A fixed component of the support helps to ensure the predictability of aid flows in line with good practice.

Variable tranche payments linked to performance. In practice, the Government will need to agree with donors their individual preferences through the JMM process.

Donors could choose to make a single tranche or multiple tranches based on progress throughout the fiscal year.  Multiple disbursements during the year helps manage risk of potentially significant unutilized cash reserves and opacity if balance sheet information is not routine. Multiple disbursements also provides positive incentives to improve cash flow management. Multiple tranches, however, increases risk of delays if donors do not disburse on time in accordance to the agreed disbursement schedule and has the potential to reduce flexibility to finance lumpy expenditures (though spending constraints managed via reimbursement provisions).

The Government and participating donors may consider agreement to program budget execution, performance indicators (of say 5% end-Mar, 20% end-June, 30% end-Sep, 60% end-Dec or based on submitted monthly cash flow forecast needs). Budget execution performance below these levels would not only trigger a discussion on budget execution performance but could also lead to the program considered off-track).

There will be a mechanism to handle under spends and protecting unspent funds.

Specific arrangements will have to be agreed and in place to manage budget support funds. There are a range of issues that will need to be considered when establishing the financial management arrangements, including how funds will be handled, how underspends in any given period will be reallocated and reported on and what protections if any development partners will require.

Efforts to maximise absorptive capacity are important.

Funding ceilings in the form of nominal amounts or as a percentage of appropriations and actual expenditure (e.g. 60% maximum for the percentage of budget support against appropriations and actual expenditure) need consideration.

A single plan, single audit and single monitoring and evaluation system adopted. This will minimize transactions costs including minimizing the administrative burden placed on the Government associated with administering grant agreements.

C) Budget and Accounting treatments, Fund Flows

Program budget support should be included in the appropriate budget papers. It is important that the budget includes the funds provided in this program and actual expenditure is included in annual reporting. This reinforces the need for the program cycle to match the budget cycle.

Transactions under the framework should be in the AFMIS general ledger.

Foreign assistance should disburse into a single Government nominated Bank Account (central bank or commercial) where funds from different donors comingle. If there is agreement to use the central bank and the TSA then comingling with appropriated own source (non-grant) funds could occur but be managed by existing mechanisms like sub-accounts or special accounts.

An annual disbursement schedule agreement will need to be established. This agreement might include provision for the Government to write to donors requesting payment and identifying special account banking information for transfer and deposit of funds.

C) Procurement

National procurement systems used in accordance with procurement policies or legislation or covered through pilot arrangements as part of the PFM reform process.

The Government and participating donors will need to agree on how to manage procurement. This could be through reporting arrangements as reflected in the Joint Monitoring Matrix, Mutually Agreeable Results targets, and program specific reporting arrangements as agreed on an annual basis.

Medium Term Resourcing Envelope

It is important to have confirmation of the medium term resourcing envelope including indicative projections for programme budget support.  Based on MoF projections included in the national budget prior to the first year of operation of the Framework.

A systematic but flexible approach for dealing with fungability and additionality concerns is desirable. This could involve the use of:

a special bank account initially to ensure unused funds are tracked and accounting controls can be used increasingly well;

dialogue based around the budget cycle to ensure the Government and development partners are in agreement about the level of resourcing and spending priorities for the budget year;

analysis is undertaken to test for side-funnelling where there is an indication that this might be happening (intentionally or unintentionally);

funding and expenditure floors and ceilings may be used as mutually agreed (with floors and ceilings being either nominal amounts or a percentage-based figure).

The Government and the development partners will also need to agree if there is to be any inclusion of ineligible expenditure items during the life of the program. Any such agreement if made should reflect an attempt to help manage reputation and political risks borne by development partners.

In-Kind and Analytical Advisory Assistance

Development partners in accordance with the Government’s strategic plans and 5-year rolling Annual Action Plans can also provide in-kind assistance. The Government would develop a technical assistance policy that makes it explicit that for this program, TA must link to gaps identified in the annual action plans.

Work needs to start now. If the Government and the development partners pursue a targeted sector, budget support framework following this broad outline there is much work to do. The preconditions for such an arrangement are not in place. A reasonable timeframe for achieving some credible preconditions and for establishing the necessary agreements would be the start of the 2017 / 1396 fiscal year.

## Attachment E: Costings and Resource Allocations

Costings by Directorate (US$)

|  | Emp. Compensation | TA Compensation | G&S | Capital | Grand Total | TA Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1.0 Office of the Minister | - | 1,260,417 | 1,462,083 | 250,417 | 2,972,917 | 2,772,917 |
| 1.1 OoM: Communications and Public Relations Directorate | - | 43,750 | 50,750 | 1,750 | 96,250 | 96,250 |
| 1.2 OoM: Correspondence Office | - | 135,417 | 157,083 | 5,417 | 297,917 | 297,917 |
| 1.3 OoM: Legal Advisors | - | 383,333 | 444,667 | 15,333 | 843,333 | 843,333 |
| 1.4 OoM: Archive Office | - | 58,333 | 67,667 | 2,333 | 128,333 | 128,333 |
| 1.5 OoM: Translation Board |  | 29,167 | 33,833 | 1,167 | 64,167 | 64,167 |
| 1.6 OoM: Protocol Office | - | 35,417 | 41,083 | 1,417 | 77,917 | 77,917 |
| 1.7 OoM: Non-Allocated Advisor Pool | - | 75,000 | 87,000 | 3,000 | 165,000 | 165,000 |
| 1.8 OoM: Office of the Chief of Staff | - | 500,000 | 580,000 | 220,000 | 1,300,000 | 1,100,000 |
|  |  |  |  |  | - |  |
| 2.0 Customs Department | - | 1,183,333 | 1,372,667 | 2,047,333 | 4,603,333 | 2,603,333 |
| 2.1 CD: Customs Support and Development | - | 750,000 | 870,000 | 1,030,000 | 2,650,000 | 1,650,000 |
| 2.2 CD: Law Enforcement | - | 200,000 | 232,000 | 8,000 | 440,000 | 440,000 |
| 2.3 CD: Customs Technical Affairs | - | 20,833 | 24,167 | 1,000,833 | 1,045,833 | 45,833 |
| 2.4 CD: Operations | - | 112,500 | 130,500 | 4,500 | 247,500 | 247,500 |
| 2.5 CD: Internal Audit Unit | - | 100,000 | 116,000 | 4,000 | 220,000 | 220,000 |
|  |  |  |  |  | - |  |
| 3.0 Revenues Department | - | 2,006,250 | 2,327,250 | 1,080,250 | 5,413,750 | 4,413,750 |
| 3.1 RD: Office of the DG (Revenue) | - | 262,500 | 304,500 | 10,500 | 577,500 | 577,500 |
| 3.2 RD: Large Taxpayers Office | - | 337,500 | 391,500 | 13,500 | 742,500 | 742,500 |
| 3.3 RD: Medium Taxpayers Office | - | 287,500 | 333,500 | 11,500 | 632,500 | 632,500 |
| 3.4 RD: Small Taxpayers Office | - | 287,500 | 333,500 | 11,500 | 632,500 | 632,500 |
| 3.5 RD: Appeals | - | 125,000 | 145,000 | 5,000 | 275,000 | 275,000 |
| 3.6 RD: Legal | - | 125,000 | 145,000 | 5,000 | 275,000 | 275,000 |
| 3.7 RD: Non-Tax Revenue | - | 225,000 | 261,000 | 9,000 | 495,000 | 495,000 |
| 3.8 RD: Technical and Provincial Liaison | - | 168,750 | 195,750 | 6,750 | 371,250 | 371,250 |
| 3.9 RD: Revenue Services and Support | - | 187,500 | 217,500 | 1,007,500 | 1,412,500 | 412,500 |
|  |  |  |  |  | - |  |
| 4.0 Treasury Department | - | 625,000 | 1,225,000 | 1,525,000 | 3,375,000 | 3,375,000 |
| 4.1 TD: Treasury Systems Development | - | 125,000 | 645,000 | 1,505,000 | 2,275,000 | 2,275,000 |
| 4.2 TD: Accounting | - | 250,000 | 290,000 | 10,000 | 550,000 | 550,000 |
| 4.3 TD: Payments | - | 250,000 | 290,000 | 10,000 | 550,000 | 550,000 |
|  |  |  |  |  | - |  |
| 5.0 Budget Department | - | 645,833 | 749,167 | 25,833 | 1,420,833 | 1,420,833 |
| 5.1 BD: Budget Execution | - | 300,000 | 348,000 | 12,000 | 660,000 | 660,000 |
| 5.2 BD: Budget Policy | - | 345,833 | 401,167 | 13,833 | 760,833 | 760,833 |
|  |  |  |  |  | - |  |
| 6.0 Admin Department | - | 931,250 | 1,080,250 | 2,037,250 | 4,048,750 | 2,048,750 |
| 6.1 AD: Procurement and General Services | - | 75,000 | 87,000 | 3,000 | 165,000 | 165,000 |
| 6.2 AD: Finance and Accounting | - | 443,750 | 514,750 | 17,750 | 976,250 | 976,250 |
| 6.3 AD: IT | - | 162,500 | 188,500 | 2,006,500 | 2,357,500 | 357,500 |
| 6.4 AD: MoF Project Implementation Unit | - | 125,000 | 145,000 | 5,000 | 275,000 | 275,000 |
| 6.5 AD: Auctions and Disposals Unit | - | 25,000 | 29,000 | 1,000 | 55,000 | 55,000 |
| 6.6 AD: Gender Unit | - | 100,000 | 116,000 | 4,000 | 220,000 | 220,000 |
|  |  |  |  |  | - |  |
| 7.0 SOE Department | - | 402,083 | 466,417 | 16,083 | 884,583 | 884,583 |
| 7.1 SD: Policy & Coordination | - | 87,500 | 101,500 | 3,500 | 192,500 | 192,500 |
| 7.2 SD: Financial Monitoring SoCs | - | 150,000 | 174,000 | 6,000 | 330,000 | 330,000 |
| 7.3 SD: Financial Monitoring SoEs | - | 89,583 | 103,917 | 3,583 | 197,083 | 197,083 |
| 7.4 SD: Divesture of State Profitable Entities and Establishment of New State-Owned Enterprises and Corporations | - | 75,000 | 87,000 | 3,000 | 165,000 | 165,000 |
|  |  |  |  |  | - |  |
| 8.0 Property Department | - | 522,500 | 606,100 | 20,900 | 1,149,500 | 1,149,500 |
| 8.1 PD: Provincial Property Directorate | - | 145,000 | 168,200 | 5,800 | 319,000 | 319,000 |
| 8.2 PD: Registration and Resolution Directorate | - | 195,000 | 226,200 | 7,800 | 429,000 | 429,000 |
| 8.3 PD: Capital Properties (Kabul) Directorate | - | 182,500 | 211,700 | 7,300 | 401,500 | 401,500 |
|  |  |  |  |  | - |  |
| 9.0 Human Resources Department | 1,000,000 | 133,333 | 2,154,667 | 5,333 | 3,293,333 | 293,333 |
| 9.1 HRD: Training & Development | - | 66,667 | 2,077,333 | 2,667 | 2,146,667 | 146,667 |
| 9.2 HRD: Recruitment Development | - | 20,833 | 24,167 | 833 | 45,833 | 45,833 |
| 9.3 HRD: Organizational Development | - | 16,667 | 19,333 | 667 | 36,667 | 36,667 |
| 9.4 HRD: Performance Appraisal & Record Keeping | 1,000,000 | 16,667 | 19,333 | 667 | 1,036,667 | 36,667 |
| 9.5 HRD: Employee Relations | - | 12,500 | 14,500 | 500 | 27,500 | 27,500 |
|  |  |  |  |  | - |  |
| 10.0 Insurance Department | - | 110,417 | 128,083 | 4,417 | 242,917 | 242,917 |
| 10.1 ID: Insurance Affairs | - | 110,417 | 128,083 | 4,417 | 242,917 | 242,917 |
|  |  |  |  |  | - |  |
| 11.0 Internal Audit Department | - | 831,250 | 964,250 | 33,250 | 1,828,750 | 1,828,750 |
| 11.1 IAD: Office of the DG | - | 387,500 | 449,500 | 15,500 | 852,500 | 852,500 |
| 11.2 IAD: Compliance and IT Audit and Fraud Investigation | - | 162,500 | 188,500 | 6,500 | 357,500 | 357,500 |
| 11.3 IAD: Budget and Treasury Audit | - | 89,583 | 103,917 | 3,583 | 197,083 | 197,083 |
| 11.4 IAD: Customs and Revenue Audit | - | 89,583 | 103,917 | 3,583 | 197,083 | 197,083 |
| 11.5 IAD: Budgetary Audit and Capacity Development (line ministries) | - | 102,083 | 118,417 | 4,083 | 224,583 | 224,583 |
|  |  |  |  |  | - |  |
| 12.0 Programs Implementation and Coordination General Directorate | - | 125,000 | 145,000 | 5,000 | 275,000 | 275,000 |
| 12.1 PICGD: Directorate for Coordination of National Priority Programs | - | 100,000 | 116,000 | 4,000 | 220,000 | 220,000 |
| 12.2 PICGD: Directorate for Policy Research | - | 25,000 | 29,000 | 1,000 | 55,000 | 55,000 |
|  |  |  |  |  | - |  |
| 13.0 Monitoring, Analysis and Reporting General Directorate | - | 50,000 | 58,000 | 2,000 | 110,000 | 110,000 |
| 13.1 MARGD: Directorate of Program Monitoring | - | 25,000 | 29,000 | 1,000 | 55,000 |  |
| 13.2 MARGD: Directorate for Analysis and Reporting | - | 25,000 | 29,000 | 1,000 | 55,000 | 55,000 |
| 14.0 Reform Implementation Management Unit (RIMU) | - | 50,000 | 58,000 | 2,000 | 110,000 | 110,000 |
| 14.1 RIMU | - | 50,000 | 58,000 | 2,000 | 110,000 | 110,000 |
|  |  |  |  |  | - |  |
| 15.0 Revenue Planning Department | - | 425,000 | 493,000 | 17,000 | 935,000 | 935,000 |
| 15.1 Revenue Analysis and Forecasting | - | 75,000 | 87,000 | 3,000 | 165,000 | 165,000 |
| 15.2 Monitoring and Evaluation of Revenue Targets | - | 75,000 | 87,000 | 3,000 | 165,000 | 165,000 |
|  |  |  |  |  | - |  |
| 16.0 Macro-Fiscal Performance Department | - | 675,000 | 783,000 | 227,000 | 1,685,000 | 1,485,000 |
| 16.1 MFPD: Fiscal Directorate | - | 116,667 | 135,333 | 4,667 | 256,667 | 256,667 |
| 16.2 MFPD: Macroeconomic Unit | - | 50,000 | 58,000 | 2,000 | 110,000 | 110,000 |
| 16.3 MFPD: Admin and Reporting Unit | - | 108,333 | 125,667 | 4,333 | 238,333 | 238,333 |
| 16.4 MFPD: Performance Management Team | - | 400,000 | 464,000 | 216,000 | 1,080,000 | 880,000 |
|  |  |  |  |  | - |  |
| 17.0 Aid Management Directorate | - | 220,833 | 256,167 | 8,833 | 485,833 | 485,833 |
| 17.1 AMD: Aid Management | - | 220,833 | 256,167 | 8,833 | 485,833 | 485,833 |
|  |  |  |  |  | - |  |
| 18.0 Office of the President | - | 175,000 | 203,000 | 7,000 | 385,000 | 385,000 |
| 18.1 National Procurement Authority (NPA) | - | 175,000 | 203,000 | 7,000 | 385,000 | 385,000 |
|  |  |  |  |  | - |  |
| 19.0 Other Partner Agencies | - | 41,667 | 48,333 | 1,667 | 91,667 | 91,667 |
| 19.1 AEITI Secretariat | - | 41,667 | 48,333 | 1,667 | 91,667 | 91,667 |
| Grand Total | 1,000,000 | 10,414,167 | 14,580,433 | 7,316,567 | 99,236,833 | 24,911,167 |

Medium Term Costings by Economic Classification (US$)

| Item | 1395/ 2016 | 1396/ 2017 | 1397/ 2018 | 1398/ 2019 | 1399/ 2020 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Emp. Compensation | 600,000 | 848,000 | 1,123,600 | 1,191,016 | 1,262,477 | 5,025,093 |
| TA Compensation | 6,248,500 | 8,831,213 | 11,701,358 | 12,403,439 | 13,147,645 | 52,332,156 |
| G&S | 8,748,260 | 12,364,207 | 16,382,575 | 17,365,529 | 18,407,461 | 73,268,033 |
| Capital | 4,389,940 | 6,204,449 | 8,220,894 | 8,714,148 | 9,236,997 | 36,766,428 |
| Unallocated |  | 2,968,000 | 6,741,600 | 8,575,315 | 10,604,806 | 28,889,722 |
| Total Excl. Unallocated | 19,986,700 | 28,247,869 | 37,428,427 | 39,674,132 | 42,054,580 | 167,391,709 |
| Grand Total | 19,986,700 | 31,215,869 | 44,170,027 | 48,249,448 | 52,659,387 | 196,281,431 |
| TA Total | 14,946,700 | 21,124,669 | 27,990,187 | 29,669,598 | 31,449,774 | 125,180,928 |

Medium Term Costings by Function Classification (US$)

| Function and function Groups | 1395/ 2016 | 1396/ 2017 | 1397/ 2018 | 1398/ 2019 | 1399/ 2020 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| # Grand Total | # 19,986,700 | # 31,215,869 | # 44,170,027 | # 48,249,448 | # 52,659,387 | # 196,281,431 |
| # General Public Services | # 19,521,950 | # 28,863,023 | # 38,805,305 | # 41,610,030 | # 44,611,622 | # 173,411,930 |
| #### GPS - Executive & legislative organs, financial & fiscal affairs, external affairs | #### 16,564,200 | #### 24,258,736 | #### 32,367,545 | #### 34,786,004 | #### 37,378,155 | #### 145,354,641 |
| #### GPS - General Services | #### 2,957,750 | #### 4,604,287 | #### 6,437,760 | #### 6,824,025 | #### 7,233,467 | #### 28,057,289 |
| #### GPS - Basic Research | #### - | #### - | #### - | #### - | #### - | #### - |
| #### GPS - R&D General public services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### GPS - General Public Services n.e.c. | #### - | #### - | #### - | #### - | #### - | #### - |
| #### GPS - Public debt transactions | #### - | #### - | #### - | #### - | #### - | #### - |
| # Defence | # - | # - | # 449,440 | # 476,406 | # 504,991 | # 1,430,837 |
| #### D - Military Defence | #### - | #### - | #### - | #### - | #### - | #### - |
| #### D - Civil Defence | #### - | #### - | #### 449,440 | #### 476,406 | #### 504,991 | #### 1,430,837 |
| #### D - R&D Defence | #### - | #### - | #### - | #### - | #### - | #### - |
| # Public Order and Safety | # 264,000 | # 1,221,120 | # 1,393,264 | # 1,476,860 | # 2,070,462 | # 6,425,706 |
| #### POS - Police Services | #### 264,000 | #### 797,120 | #### 943,824 | #### 1,000,453 | #### 1,060,481 | #### 4,065,878 |
| #### POS - Fire Protection Services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### POS - Law Courts | #### - | #### - | #### - | #### - | #### - | #### - |
| #### POS - Prisons | #### - | #### - | #### - | #### - | #### - | #### - |
| #### POS - Public Order and Safety n.e.c. | #### - | #### 424,000 | #### 449,440 | #### 476,406 | #### 1,009,982 | #### 2,359,828 |
| # Economic Affairs | # 200,750 | # 707,727 | # 1,724,258 | # 2,304,120 | # 2,442,367 | # 7,379,221 |
| #### EA - General Economic, Commercial and Labour Services | #### 145,750 | #### 205,993 | #### 272,941 | #### 289,318 | #### 306,677 | #### 1,220,679 |
| #### EA - Agriculture, Forestry, Fishing & Hunting | #### - | #### 424,000 | #### 449,440 | #### 476,406 | #### 504,991 | #### 1,854,837 |
| #### EA - Fuel and Energy | #### 55,000 | #### 77,733 | #### 552,437 | #### 585,583 | #### 620,718 | #### 1,891,471 |
| #### EA - Mining, Manufacturing & Construction | #### - | #### - | #### 449,440 | #### 952,813 | #### 1,009,982 | #### 2,412,234 |
| #### EA - Transport | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EA - Communication | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EA - Other industries | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EA - R&D Economic Affairs | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EA - Economic Affairs n.e.c. | #### - | #### - | #### - | #### - | #### - | #### - |
| # Environmental Protection | # - | # - | # - | # - | # 504,991 | # 504,991 |
| #### EP - Waste Management | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EP -Waste Water Management | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EP -Pollution Abatement | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EP -Protection of Bio-diversity and Landscape | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EP -R&D Environmental Protection | #### - | #### - | #### - | #### - | #### - | #### - |
| #### EP -Environmental Protection n.e.c. | #### - | #### - | #### - | #### - | #### 504,991 | #### 504,991 |
| # Housing and Community Development | # - | # 424,000 | # 449,440 | # 952,813 | # 1,009,982 | # 2,836,234 |
| #### HCD - Housing Development | #### - | #### - | #### - | #### 476,406 | #### 504,991 | #### 981,397 |
| #### HCD - Community Development | #### - | #### 424,000 | #### 449,440 | #### 476,406 | #### 504,991 | #### 1,854,837 |
| #### HCD - Water Supply | #### - | #### - | #### - | #### - | #### - | #### - |
| #### HCD - Street Lighting | #### - | #### - | #### - | #### - | #### - | #### - |
| #### HCD - R&D Housing and community amenities | #### - | #### - | #### - | #### - | #### - | #### - |
| #### HCD - Housing and community amenities n.e.c. | #### - | #### - | #### - | #### - | #### - | #### - |
| # Health | # - | # - | # 449,440 | # 476,406 | # 504,991 | # 1,430,837 |
| #### H - Medical Products, appliances and equipment | #### - | #### - | #### - | #### - | #### - | #### - |
| #### H - Outpatient Services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### H - Hospital Services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### H - Public Health Services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### H - R&D Health | #### - | #### - | #### - | #### - | #### - | #### - |
| #### H - Health n.e.c. | #### - | #### - | #### 449,440 | #### 476,406 | #### 504,991 | #### 1,430,837 |
| # Recreation, Culture, Religion | # - | # - | # - | # - | # - | # - |
| #### RCR - Recreational and sporting services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### RCR - Cultural Services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### RCR - Broadcasting and publishing services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### RCR - Religious and Other Community Services | #### - | #### - | #### - | #### - | #### - | #### - |
| #### RCR - R&D Recreation, Culture and Religion | #### - | #### - | #### - | #### - | #### - | #### - |
| #### RCR - Recreation, culture and religion n.e.c. | #### - | #### - | #### - | #### - | #### - | #### - |
| # Education | # - | # - | # 449,440 | # 476,406 | # 504,991 | # 1,430,837 |
| #### E - Pre-primary and primary education | #### - | #### - | #### - | #### - | #### - | #### - |
| #### E - Secondary education | #### - | #### - | #### - | #### - | #### - | #### - |
| #### E - Post-secondary non-tertiary education | #### - | #### - | #### - | #### - | #### - | #### - |
| #### E - Tertiary education | #### - | #### - | #### - | #### - | #### - | #### - |
| #### E - Education not definable by level | #### - | #### - | #### - | #### - | #### - | #### - |
| #### E - Subsidiary services to education | #### - | #### - | #### - | #### - | #### - | #### - |
| #### E - R&D education | #### - | #### - | #### - | #### - | #### - | #### - |
| #### E - Education n.e.c. | #### - | #### - | #### 449,440 | #### 476,406 | #### 504,991 | #### 1,430,837 |
| # Social Protection | # - | # - | # 449,440 | # 476,406 | # 504,991 | # 1,430,837 |
| #### SP - Sickness and disability | #### - | #### - | #### - | #### - | #### - | #### - |
| #### SP - Old age | #### - | #### - | #### - | #### - | #### - | #### - |
| #### SP - Survivors | #### - | #### - | #### - | #### - | #### - | #### - |
| #### SP - Family and children | #### - | #### - | #### - | #### - | #### - | #### - |
| #### SP - Unemployment | #### - | #### - | #### 449,440 | #### 476,406 | #### 504,991 | #### 1,430,837 |
| #### SP - Housing | #### - | #### - | #### - | #### - | #### - | #### - |
| #### SP - Social exclusion n.e.c. | #### - | #### - | #### - | #### - | #### - | #### - |
| #### SP - R&D Social protection | #### - | #### - | #### - | #### - | #### - | #### - |
| #### SP - Social protection n.e.c. | #### - | #### - | #### - | #### - | #### - | #### - |

This plan summarises outcomes from team level 5-year rolling plans developed by teams and approved by Directors, DGs and ultimately the Minister for Finance.

For details on the team based performance framework see the paper “Implementation of the Public Financial Management Roadmap II: Achieving a Performance Culture in a Conflicted Affected Afghanistan” (the implementation strategy paper) produced by the Government in 2015.

In the context of this plan, the Government refers to “risk” as the risk of failure or of not achieving reforms.

We present this framework in more detail in the paper: “Implementation of the PFMRII: Achieving a Performance Culture in a Conflict Affected Afghanistan” (GoIRA, November 2015).

GoIRA, 2014, “Realizing Self-Reliance - Commitments to Reforms and Renewed Partnership” GoIRA, Kabul, Afghanistan.

Implementation of the PFMRII: Achieving a Performance Culture in a Conflict Affected Afghanistan (GoIRA, November 2015).

As developed and driven by the g7+ to which Afghanistan is a member.

Collins Dictionary http://www.collinsdictionary.com/dictionary/english/rolling-plan

Diamond, 2013, “Good Practice Note on Sequencing PFM Reforms”, PEFA Secretariat, Washing DC, USA. A successful team-based performance management has been employed in the MOF in Timor-Leste between 2012 and 2015 with good results. See www.mof.go.tl

OGP launched in 2011 to provide an international platform for domestic reformers committed to making their governments more open, accountable, and responsive to citizens.  Since then, OGP has grown from 8 countries to 66 participating countries. More information is at: http://www.opengovpartnership.org/